## 1. Executive Summary
Staybooker Booking Engine — Stakeholder Report (June 2026)
Prepared for the CEO, founders, investors and stakeholders. What has been solved, what is in progress, what risks are coming as we grow, how the product stays fast and crash-proof at scale, and the team needed to sustain it.
Topic | Detail
WHAT THIS REPORT CONTAINS
Sheet 2 — Problems Solved | 74 issues fixed so far (6 Critical, 38 High, 30 Medium) across the project's history. Each issue shows what would have happened to the business if it had reached production.
Sheet 3 — Features Built | 37 major product features delivered alongside the bug fixing — multi-property chains, loyalty, the Revenue Engine, OTA-style booking widgets, a GST/tax engine, WhatsApp & Google AI agents, a full Super Admin platform console, subscriptions & feature-gating, and more.
Sheet 4 — Work In Progress | Critical items currently being worked on.
Sheet 5 — Future Risks | 13 real-world scenarios that WILL come as the business grows (100 users at once, payment failures, DDoS attacks, data growing to GBs) — what protection already exists and what still needs to be built.
Sheet 6 — Team & Hiring | What a Tech Lead / Backend / Frontend / Database developer actually does, in simple language — who owns which part of the product as it grows, with a suggested hiring order and a note for stakeholders.
Sheet 7 — Engineering Plan by Role (NEW) | The detailed, day-to-day work each developer does as we grow — how APIs are kept fast and cheap (optimisation), and the constant bug-hunting that keeps the server stable. This is the 'what exactly will they do all day' answer.
Sheet 8 — Silent Bugs & Server Stability (NEW) | The most dangerous bugs are the quiet ones — no error on screen, but the server slowly leaks, stalls or crashes. This sheet lists that class of risk, what already protects us, and why the whole software will NOT go blank.
Sheet 9 — Scaling to Large Data (NEW) | When a hotel has 2–3 years of bookings (GBs of data), it must still travel database → backend → browser in milliseconds and the page must never freeze. This sheet shows the speed budget and the plan to hold it.
Architecture diagram (NEW) | A full visual map of the system — Staybooker_Architecture.excalidraw at the project root — showing how a request flows from the guest's browser through Cloudflare, the backend, Redis and the database, and back. Useful when onboarding any new engineer or stakeholder.
KEY NUMBERS
Issues fixed till date | 74 (source: full git history of 890 commits + work_log_tracker.csv, up to 16-Jun-2026; merged across PRs up to #90)
Critical issues fixed | 6 — payment secret key leak, payment amount tampering, permanent admin token, AI assistant crash, staff privilege escalation, and the booking-widget code-execution (RCE/XSS) sink.
Security audit coverage | A full security/performance audit found 36 findings (1 Critical, 12 High, 14 Medium, 9 Low). The Critical issue and most High findings are fixed; the rest are tracked openly in Sheets 4 and 5.
Automated tests added | Close to 300 automated test cases (security, payments, booking, roles, rate limits, Redis failover, chain isolation, promotions) that run on every code change (CI/CD), with dependency vulnerability (CVE) scanning.
Money saved (examples) | Payment tampering fix: a guest could pay Rs.1 and get a Rs.10,000 booking confirmed. AI cost fix: a bug was sending traffic to an AI model 10x more expensive than needed on the public chatbot. Tax validation fix: invalid tax setup could produce wrong bills for every guest.
Stability posture | The app is built to fail SAFE: if Redis drops it falls back to in-memory limits; if a data fetch fails the guest sees a Retry button, never a blank page; security and money checks 'fail closed' (deny), while the screen 'fails soft' (keeps working). Details in Sheets 8 and 9.
WHAT'S NEW SINCE 11-JUN
Revenue Engine shipped | Dynamic pricing (occupancy/lead-time rules wired to real charges), abandoned-booking recovery (WhatsApp + email, hourly scheduler), and a loyalty wallet with stay offers and upsell hub — a whole new revenue surface (PR #80).
Chain & promotions | Chain-wide upsell broadcast, package validity windows, and seasonal auto-apply promotions at hotel and chain level (PR #88).
Stability & crash fixes | Fixed a blank-white-screen crash on deploy (S-48), two booking-flow 500 crashes (S-46, S-47), a dead recovery scheduler (S-49), broken deploys/migrations (S-54, S-56), and removed a widget code-execution security hole (S-50).
ONE-LINE MESSAGE FOR THE CEO
Bottom line | The product is stable today and hoteliers' data is safe — and it is moving fast: 58 issues fixed, 23 features shipped, and a full Revenue Engine added since launch. The hiring need comes from exactly this momentum: as hotels, traffic and data scale up, each layer — database, backend, frontend — needs a dedicated owner so the speed, safety and crash-proofing stay where they are today. Sheets 7-9 spell out, in plain language, the ongoing engineering that keeps it that way.

## 2. Problems Solved
Problems Solved (with Business Impact)
Source: work_log_tracker.csv + Security Audit Report. The 'If this had reached production' column shows the damage each fix prevented.
ID | Problem (Simple Language) | What Was Happening Technically | If This Had Reached Production... (Business Impact) | How It Was Fixed | Severity | Fixed On
S-01 | The hotel's secret payment key (Razorpay) was visible on the public website | Any anonymous visitor could read the hotel's razorpay_key_secret through the public hotel API | Anyone could have used it to issue refunds from the hotel's payment account or fake payment verifications. The hotel loses money, we carry the legal responsibility, and the Razorpay account could be suspended. | All secrets are now AES-256 encrypted in Supabase Vault. Public APIs mask them. The secret never reaches the browser. | Critical | 09-Jun
S-02 | A guest could send any amount they wanted and get the booking marked as 'paid' | The payment order API trusted the amount sent by the browser; the server never verified it | A guest could pay Rs.1 and get a Rs.10,000 booking CONFIRMED. The hotel would have to honour the room without receiving the money. Direct revenue loss and loss of hotel trust. | The amount is now always calculated on the server from the booking total. Whatever the client sends is ignored. | Critical | 08-Jun
S-03 | The admin 'impersonation' login token never expired | When a super-admin logged into a hotel's account, that token was permanent (no expiry) | If that token ever leaked (email, log file, lost laptop), whoever had it would keep owner-level access to that hotel indefinitely — bookings, payments, guest data. | Tokens now expire in 15-30 minutes; the verifier rejects any token without an expiry. | Critical | 08-Jun
S-04 | The AI Assistant was completely crashing (critical bug) | A logger was not defined in the code — the smart tool selector crashed with an error every time | Every time a hotelier opened the AI assistant, they got an error. A premium feature we charge for was dead — paying customers would churn. | Fixed the logger and added a regression test so it cannot happen again. | Critical | 10-Jun
S-05 | Hotel STAFF (e.g. a receptionist) could do everything an OWNER can via the API | Role checks existed only in the frontend menu, not on the backend API | Any staff account — by mistake or misuse — could change rates, delete rooms, or alter payment keys in settings. Sensitive controls were not limited to the owner/manager. | Backend role gates (OWNER/MANAGER required) added, plus 76 role-access test cases. | Critical | 08-Jun
S-06 | Hotel A could use Hotel B's private promo codes | The promo validation API did not check which hotel/chain the code belonged to | One hotel could apply another hotel's discount codes. Revenue leakage and loss of trust in the platform (a serious failure for a multi-hotel system). | Promo lookup is now strictly limited to the requesting hotel's own chain. | High | 06-Jun
S-07 | There was no tenant isolation at the database level | Everything depended only on application code; the database had no Row Level Security (RLS) | A single code bug would let Hotel A see Hotel B's guests and bookings. Data breach, GDPR/DPDP penalties, customer loss. | Postgres RLS policies on every tenant table — the database itself refuses to return another hotel's data (a second lock). | High | 09-Jun
S-08 | All hotel secrets (WhatsApp, email, AI keys) were stored as plain text in the database | If the database or a backup ever leaked, all keys were readable | One database leak = every hotel's WhatsApp, email and payment accounts compromised. A mass-scale breach that could end the business. | All secrets are AES-256-GCM encrypted in Supabase Vault; never stored or logged as plain text. | High | 09-Jun
S-09 | The public AI chatbot used a 10x more expensive model whenever an error occurred | The error-fallback path switched to a large 70B model instead of the cheap 8B model | Any anonymous user could trigger an error storm and push our AI bill into lakhs (a cost attack). | The fallback is now locked to the cheap model; a per-hotel daily AI quota is also in place. | High | 10-Jun
S-10 | Error messages were leaking internal system details | When the AI endpoint crashed, the raw error text (file paths, library names) was sent to the user | An outsider could learn internal system details (libraries, versions), which makes planning an attack easier. | Users now see generic error messages; details go only to server logs. | High | 10-Jun
S-11 | Guest emails/IDs were being printed in production logs (PII leak) | The login flow logged email + user ID at INFO level | Logs go to third-party services — personal data leaking there is a privacy violation and a DPDP fine risk. | PII logging moved to DEBUG level; production runs at WARNING level only. | High | 10-Jun
S-12 | Post-booking emails and channel sync were silently failing | The background task helper was calling tasks the wrong way — work was silently skipped | Guests would not receive confirmation emails and channel sync would not run → double bookings on OTAs, upset guests, more support calls. | Fixed the background task pattern — tasks now run reliably and errors are visible. | High | 08-Jun
S-13 | The guest list API loaded ALL data with no limit | GET /guests was unbounded — 100,000 guests would crash the server | Opening the page for a large hotel would hang the page or crash the server with out-of-memory. In peak season, system down = direct booking loss. | Pagination (limit + offset) is now mandatory; database indexes added on hot columns. | High | 08-Jun
S-14 | Browser autofill was silently overwriting real API keys | In the admin integrations form, the browser injected saved passwords into the key fields | The moment an admin clicked Save, the hotel's correct payment/WhatsApp keys were corrupted — payments fail, 'site is down' complaints. | Anti-autofill pattern: fields are locked by default and only become editable on an explicit click. | High | 09-Jun
S-15 | The Rate Shopper was showing false 'SOLD OUT' statuses | When a competitor's price element was not found, a full-page fallback picked up wrong data | Hoteliers would make pricing decisions on wrong market data — selling rooms too cheap or too expensive — and would lose confidence in the product. | Fixed the scoping logic; when data is missing we show a dash, never a wrong status. | High | 10-Jun
S-16 | Rate Shopper usage billing was undercounting | When a request timed out or errored, the usage record was skipped | We pay the data vendor for every attempt, but were not counting it on our side — a silent margin loss. | Every attempt is now recorded and billable, regardless of outcome. | High | 07-Jun
S-17 | Loyalty program settings could be changed by STAFF | The loyalty program update endpoint had no role check | Any staff account could change the points-to-rupee ratio and credit points to a personal email — a misuse risk. | OWNER/MANAGER role now required; the checkout task is also safely wrapped. | High | 08-Jun
S-18 | Loyalty points could be credited twice due to a race condition | Points were credited at check-out without a lock | A guest's points credited twice → loyalty liability grows, financial reports become wrong. | Redis locks added; point deduction now happens atomically inside a database transaction. | High | 06-Jun
S-19 | Real-time WebSocket connections could be opened without authentication | The new live-updates channel could be connected without verifying the login token (caught during design) | Anyone could listen to a hotel's live booking events — guest data leak. | The connection is accepted only after the login token (JWT) is verified. | High | 08-Jun
S-20 | One slow web search could block the entire AI server | The AI assistant's web search ran synchronously — one slow call froze all other requests | One user's slow query would hang the AI for every hotelier. 'The system is slow' complaints. | Search now runs in a background thread with a hard 8-second timeout. | Medium | 10-Jun
S-21 | After a cancellation, the availability cache still showed old data | The rate cache was not cleared after a booking or cancellation | A guest would see a sold room as 'available', book it, and the hotel would have to cancel manually. Bad reviews. | Cache is now cleared and a version counter is bumped after every booking/cancellation. | Medium | 08-Jun
S-22 | Heavy libraries were loading on every server start | Email/PDF libraries were imported at the top of always-loaded files — slow startup, more memory | Slow server boot = longer downtime during every deploy; higher RAM costs. | Lazy imports — libraries load only when actually needed. | Medium | 08-Jun
S-23 | A 962-line analytics file was impossible to maintain | All analytics lived in one giant file — every change was risky and hard to review | Every new feature risked breaking old ones; new developer onboarding would be slow. | Split into 4 clean modules; availability and competitors modules also split into packages. | Medium | 08-Jun
S-24 | Code changes could be merged without running tests | CI/CD ran only on the main branch; pull requests were not tested | Broken code could reach production — every deploy carried avoidable risk. | Backend + frontend CI now runs on every pull request, plus a compile gate. | Medium | 10-Jun
S-25 | Rate Shopper scraping was failing half the time | The vendor API payload was wrong; concurrent bursts caused blocks; there was no retry logic | A feature we sell as premium was unreliable — customers would cancel. | Sequential scraping + retry/backoff + session rotation + corrected payload. Runtime cut from ~7 min to ~4 min. | Medium | 08-10 Jun
S-26 | Hoteliers could not tell whether a scrape was running or stuck | Nothing updated in the UI until the full 7-day scrape finished | Users assumed the feature was broken; support tickets piled up. | Live per-day progress — the chart updates as each day's data arrives. | Medium | 07-Jun
S-27 | In multi-hotel chains, one brand's loyalty points could mix with another brand's | The loyalty schema had no chain-level isolation | Brand A's points redeemed at Brand B — a financial mess across clients. | Chain-level isolation added, with a unique index per (guest email, chain). | Medium | 06-Jun
S-28 | The loyalty discount at checkout was calculated in the browser | The maximum redeemable discount was enforced on the frontend only | A guest could edit the value in the browser and take a 100% discount. | The maximum discount is now enforced on the server; the points balance is locked in the database. | High | 06-Jun
S-29 | The concierge AI chat could access data from other hotel chains | The chat session had no chain-scope validation | A guest could extract another brand's hotel information through the chatbot. | Chain validation added in the chat router; AI tools only see the verified hotel's data. | High | 06-Jun
S-30 | The database security migration was targeting the wrong schema | Custom functions were placed in the Supabase-managed 'auth' schema — the migration would fail | The security layer would never actually deploy — all the RLS protection would exist only on paper. | Functions moved to the public schema; safe re-run guards and proper permissions added. | High | 09-Jun
S-31 | A Rate Shopper scrape could not be stopped once started | A scrape started by mistake would burn the full vendor cost before finishing | Every accidental run = vendor cost. The hotelier had no control. | Stop button added with a cancel flag; only the days actually attempted are billed. | Medium | 07-Jun
S-32 | The data vendor's name (Decodo) was visible to hoteliers | Internal vendor details were exposed in errors and the UI | Hoteliers could go directly to the vendor; damages our white-label image. | Rebranded as Staybooker OTA Analytics; vendor name removed from everything user-facing. | Medium | 07-Jun
S-33 | AI usage was not being tracked on some code paths | Some AI agent runs did not record their token usage | Our per-hotel AI cost accounting was wrong — pricing decisions were blind. | Usage is now recorded after every run; quotas are driven by this data. | Medium | 10-Jun
S-34 | The public booking widget showed FAKE 'Sold Out' labels and made-up calendar prices | A leftover demo hack marked the 13th of every month as 'Sold Out' and showed fabricated per-day prices in the calendar | Real guests were being turned away from available rooms (lost bookings every month on the 13th) and shown prices that were simply not true — a legal/consumer-trust problem. | Fake logic removed; the calendar now shows only the real starting price; availability and price are confirmed server-side. | High | 10-Jun
S-35 | The booking widget was broadcasting checkout data to ANY website embedding it | Widget messages used a wildcard ('*') target — any page embedding our widget could read booking/checkout data | Any website embedding our widget could read guests' booking details — an unintended data exposure through our own product. | Messages are now locked to the verified parent website's origin only. | High | 10-Jun
S-36 | A temporary network error showed guests a permanently blank room-selection page | One failed data fetch blanked the whole page; optional add-ons could also block the page from loading | Guest sees a white page mid-booking → closes the tab → booking lost. No error, no retry, no explanation. | Added a clear error message with a Retry button; add-ons now load separately so their failure cannot blank the page. | Medium | 10-Jun
S-37 | Guests could search with empty or reversed dates (check-out before check-in) | The booking widgets did not validate the date range before navigating to the rooms page | Guests landed on broken/empty room pages — confusing experience, dropped bookings. | Date range is validated before the search runs. | Medium | 10-Jun
S-38 | The busiest public query (availability search) had no composite database index | Every availability check scanned bookings without an optimal index on (hotel, status, dates) | As bookings grow, the most-hit public query slows down first — slow search = lost guests. | Composite index added on bookings (hotel_id, status, check_in, check_out). | Medium | 10-Jun
S-39 | If Redis went down, the AI spending limit silently turned OFF | The per-hotel AI quota was checked in Redis; when Redis was unavailable the check passed everything (fail-open) | During any Redis outage, chatbot spam could run an unlimited AI bill. | Quota now fails CLOSED: an in-process daily cap takes over whenever Redis is unavailable. | High | 10-Jun
S-40 | Rate limits could be bypassed by faking the visitor's IP address | The rate limiter trusted the first IP in the X-Forwarded-For header, which can easily be faked | Every IP-based protection (login attempts, booking spam, AI limits) was bypassable with one fake header. | Trusted-proxy aware IP extraction (TRUSTED_PROXY_COUNT) — spoofed header prefixes are ignored. | High | 10-Jun
S-41 | Invalid tax settings could be saved, producing wrong bills | The tax form accepted negative amounts, out-of-range rates and inverted slab ranges; the inclusive-tax calculator could divide by zero (NaN) | Wrong tax on every invoice = wrong bills to guests and wrong GST records — financial and compliance damage. | Validation rejects bad slabs before save; the live calculator is guarded against NaN. | High | 10-Jun
S-42 | Password changes and uploads had no rate limit (brute-force risk) | Authenticated mutating routes (password change, team-member create, file upload, reports) had no per-user caps | Repeated password-change attempts could be used for account takeover; upload/report endpoints could be abused to run up server costs. | Rate limits added: password change 5/hr, team creation 10/hr, uploads 20/hr, reports 30/min — shared across all servers via Redis. | High | 11-Jun
S-43 | The team-user list was unbounded and reports could scan unlimited date ranges | GET /users loaded every row with no limit; the occupancy report accepted any date range (e.g. 10 years) | Large accounts would hang the page; one heavy report could slow the database for every hotel. | Pagination added (limit ≤ 200 + offset); occupancy reports capped at 365 days. | Medium | 11-Jun
S-44 | One Redis hiccup permanently disabled shared locks and payment idempotency until restart | On the first Redis failure the client switched to per-process memory until a restart — distributed locks, payment idempotency and rate limits silently degraded | After any brief Redis blip: duplicate scheduled jobs, possible duplicate payment processing, rate limits split per server — all silently, until someone restarted the app. | Self-healing reconnect: 30-second back-off then automatic recovery; memory fallback only during the outage. | High | 11-Jun
S-45 | Rate Shopper requests were being blocked by the OTA's bot protection (Akamai 613) | A geo parameter in the scraping payload triggered Akamai blocks; currency could come back in the wrong unit | The premium rate-intelligence feature would fail repeatedly while still costing us vendor fees per attempt. | Payload corrected (geo removed, INR forced via URL parameter); retries and session rotation retained. | Medium | 11-Jun
S-46 | The loyalty check could crash the public booking page for some guests | The loyalty lookup used scalar_one_or_none(), which throws when a guest matches more than one loyalty row | A guest pressing 'check loyalty' could hit a 500 error mid-booking — a silent server crash that only appears for certain data, dropping bookings with no error anyone could easily reproduce. | Switched to .scalars().first() with a clear preferred-row ordering; added a regression test for the exact path. | High | 14-Jun
S-47 | Creating or cancelling a public booking could crash with a 500 | The code read super_admin.phone (a field that does not exist) and WhatsApp settings that were never defined | The core revenue action of the whole product — creating/cancelling a booking — could fail server-side, silently, for everyone. | Admin alert number moved to server config (env); WhatsApp service aligned to the real settings; two unused admin lookups removed (also fewer DB queries per booking). | High | 15-Jun
S-48 | The whole app could load as a blank white screen after a deploy | A production build optimisation (Vite manualChunks) broke React's context loading and crashed the app to a blank page | Guests and hoteliers would open the site to a completely blank screen — the worst possible failure, with no error and no way forward. | Reverted the unsafe bundling change and added instant-load placeholders so the first paint is never empty. | High | 15-Jun
S-49 | Abandoned-booking recovery was built but never actually ran | The recovery feature had no scheduled job, so unpaid bookings always aged past the 72h window un-nudged | A revenue-recovery feature we built was silently dead — incremental bookings left on the table every day with no one noticing. | Added an hourly Redis-locked scheduler that runs the sweep on exactly one server and honours each hotel's opt-in. | Medium | 15-Jun
S-50 | The booking widget could run attacker-supplied code on the hotel's site (RCE/XSS) | A 'custom JS' setting was executed via new Function()/eval on the public widget; widget CSS and chat messages were under-validated | A malicious or compromised setting could run arbitrary code in every guest's browser on the hotel's own domain — a severe security hole. | Removed the code-execution sink entirely; the public API no longer returns custom JS; iframe sandboxed; CSS sanitised (strips url()/@import/expression/script); chat postMessage locked to the referrer origin; inactive hotels return 404; guest message length capped. | Critical | 15-Jun
S-51 | Two guests could spend the same promo / loyalty balance at once | Promo-code and loyalty redemption read-then-wrote without a row lock (a race condition) | Under concurrent checkouts the same discount or points balance could be spent twice — direct revenue leakage and wrong loyalty liability. | Redemption now takes SELECT FOR UPDATE row locks; AI lead inputs are length-bounded as well. | High | 15-Jun
S-52 | A newly created property could be saved without its brand (chain) link | The property-create path did not inherit chain_id from the logged-in user | A property could end up unlinked or wrongly associated across tenants — a multi-tenant isolation risk and broken brand dashboards. | chain_id is now inherited from the authenticated user on creation; the superadmin add-property path also sets address fields correctly. | High | 14-Jun
S-53 | Loyalty read endpoints had no role check | GET /loyalty/program and /loyalty/guests were missing the role guard the write endpoints already had | Any staff account could read the loyalty program configuration and the guest list — an authorization gap on read (a trap we watch for everywhere). | require_hotel_role added to both GET endpoints. | Medium | 14-Jun
S-54 | The frontend could not deploy at all (Cloudflare Pages broken) | A stray git submodule reference (decodo-api-docs) broke every Cloudflare Pages build | No frontend deploys could ship — the product could not be updated for customers until it was fixed. | Removed the broken submodule gitlink; deploys restored. | Medium | 15-Jun
S-55 | The frontend production build was silently broken on the branch | A new widget tab imported a UI component (accordion) whose file was never committed — 'vite build' failed with a missing-file error | The next release would have failed to build with no obvious cause — exactly the kind of quiet break that blocks a deploy at the worst time. | Added the missing standard component (the dependency was already present) and verified with a full local build. | Medium | 16-Jun
S-56 | Some database columns existed in code but not in the live database | Migrations for loyalty milestones and competitor-rate columns were missing from the deploy path | Any query touching those columns would crash in production while passing locally — a hidden landmine as features rolled out. | Added the missing migrations so the live schema matches the code. | High | 15-Jun
S-57 | Hotel listings and sister-hotel suggestions always showed a blank city | City was read as a direct attribute, but it is stored inside the address JSON dict | Guests saw blank locations on chain pages and recommendations — it looks broken and quietly hurts trust and conversion. | All three hotel-listing endpoints now read city from the address dict. | Medium | 14-Jun
S-58 | Valid bookings were sometimes rejected over a 1-rupee rounding gap | The client/server price match used a flat +/-5 INR tolerance that failed on percentage-based dynamic prices | Guests with legitimate prices could be blocked at checkout by a tiny rounding difference — silent lost bookings. | Tolerance is now max(Rs.5, 1%) and the calendar pricing note is clearer. | Medium | 15-Jun
EARLIER FOUNDATIONAL FIXES (May – early June 2026) — security, crashes and correctness fixed before the June audit
S-59 | The public booking page crashed for guests (blank/white page) more than once | React runtime errors (#300 and a hooks-rule violation in a booking widget) crashed the page render | Guests opening the booking page could see a blank or broken page and leave — lost bookings with no error trail. | Fixed the React errors and hook usage; added guards so one widget can't crash the whole page. | High | 02-03 Jun
S-60 | The backend could crash on startup | Superadmin import errors, a sync/async mismatch and an undefined router crashed the server on boot | A bad deploy would take the whole API down — every hotel offline until someone noticed. | Fixed the imports, converted to async correctly, and removed the undefined router. | High | May 12-Jun 01
S-61 | The rooms page crashed with a 'Form is not defined' error | A circular dependency loaded a dialog before its form was ready | Hoteliers couldn't manage rooms — a core daily task was broken. | Lazy-loaded the dialogs to break the circular import. | Medium | 14-May
S-62 | The public booking page crashed on newly created rooms | New rooms weren't handled in the availability path and the rate cache wasn't invalidated | Brand-new inventory couldn't be booked — directly blocking sales of the newest rooms. | Fixed the availability handling and added real-time rate-cache invalidation. | High | 23-May
S-63 | The guest chatbot crashed on availability follow-up questions | The Llama model returned a tool_use_failed error that wasn't handled | A premium guest feature broke mid-conversation, frustrating guests. | Added handling for the failure path so the chat recovers gracefully. | Medium | 03-Jun
S-64 | Database migrations could fail on deploy (divergent Alembic heads) | Two migration branches diverged and some migrations weren't idempotent | A deploy could half-apply the schema and break production. | Merged the migration heads and made migrations safe to re-run. | High | 03-Jun
S-65 | Switching between properties could briefly show another property's data | Browser-side caching and a backend cache-key bug served stale, cross-property data | A hotelier could momentarily see the wrong hotel's numbers — a trust and isolation concern. | Disabled unsafe API caching, fixed the cache key, and moved to instant SPA navigation. | High | 04-05 Jun
S-66 | Cross-tenant data-isolation gaps in several endpoints (IDOR) | Some endpoints didn't fully scope queries to the caller's hotel/chain (TEN-02/04/05) | One hotel could potentially reach another's data — a serious multi-tenant breach risk. | Tightened scoping on every affected endpoint to the caller's own tenant. | High | 05-Jun
S-67 | Role-based access was defined but not actually enforced on some routes | RBAC existed in code but several routes never checked it (AZ-01/02/03) | Staff-level accounts could reach owner-level actions — privilege misuse. | Enforced the role checks on every affected route. | High | 05-Jun
S-68 | AI spend on public/agent paths was unbounded | Some LLM calls had no token or call ceiling (AI-01/02/04) | A traffic spike or abuse could run the AI bill up sharply. | Added token floors, tool-call limits and history caps across the AI paths. | High | 05-Jun
S-69 | Reports and analytics could show wrong numbers | Booking-source attribution and several analytics calculations were incorrect | Hoteliers would make decisions on wrong data and lose trust in the product. | Corrected the attribution and the analytics math; added tests. | Medium | 04-Jun
S-70 | Dashboards were slow and overloaded the database (N+1 queries) | Pages fired many small queries instead of one batched query; hotel info wasn't cached | As data grew, dashboards would slow for everyone and strain the database. | Batched the queries, added caching and parallelised integration calls. | Medium | 02-04 Jun
S-71 | Responses had no security headers | Missing HSTS, CSP, X-Frame-Options and X-Content-Type-Options | The app was more exposed to clickjacking, content-sniffing and mixed-content attacks. | Added enterprise security headers across all responses. | Medium | 16-May
S-72 | A null widget-config value could crash the embedded booking widget | Missing null-safety on widget configuration and chat | The widget could break on a hotel's own website, in front of their guests. | Hardened the config handling and chat resilience. | Medium | 04-May
S-73 | The AI usage dashboard was stuck on 'Loading…' / 'Couldn't load usage' | Subscription AI-limit columns were missing and usage lived only in Redis | Hoteliers couldn't see what they were paying for, and data vanished on a Redis blip. | Added the missing columns and made AI usage durable in Postgres. | Medium | 12-Jun
S-74 | Guests couldn't reset their password reliably | The reset flow didn't fully support PKCE/implicit hand-off and recovery redirects | Locked-out users couldn't get back in — support load and churn. | Completed the reset flow (PKCE/implicit, recovery redirect, in-profile change). | Medium | 05-Jun

## 3. Features Built
Major Features Delivered (Not Just Bug Fixes)
Source: work_log_tracker.csv. This is product value built in parallel with the security/stability work.
# | Feature | What It Does (Simple Language) | Business Value | Built Safely (Security/Cost Controls Included)
1 | Multi-property chain support | One brand owner can manage many hotels under one login: a consolidated chain dashboard with revenue, bookings and room-nights per hotel. | Lets us sell to hotel GROUPS, not just single properties — bigger contracts. | Only the chain OWNER can see consolidated data; every query validates the user belongs to that chain.
2 | Loyalty program (earn & burn points) | Guests earn points on every stay (1 point = Rs.1) and redeem them at checkout. Works across all hotels of the same brand. | Repeat bookings and direct-booking incentive — guests skip OTAs to keep their points. | Points credited with locks (no double credit); max discount enforced on the server; brand-level isolation so points never leak across brands.
3 | Chain-wide promo codes | A brand can run one discount code across all of its hotels. | Brand-level marketing campaigns become possible. | Codes validated strictly within the owning chain — Hotel A cannot use Hotel B's codes.
4 | Sister-hotel recommendations | When a hotel is sold out, the booking widget suggests available sister hotels from the same brand. | A sold-out date becomes a transfer of revenue to a sister property instead of a lost guest. | Recommendations cached (10 min) to keep searches fast; only same-chain, active hotels are shown.
5 | AI guest concierge with memory | The guest chatbot remembers past stays, preferences and special requests across all the brand's hotels. | Personalised guest experience — a premium feature competitors charge heavily for. | Only same-chain stay history is used; token usage capped to control AI cost; PII guarded.
6 | Rate Shopper (OTA rate intelligence) | Tracks competitors' prices on MakeMyTrip/OTAs day by day, with live progress, a stop button, auto-sync scheduling and market analysis charts. | Hoteliers price their rooms with real market data — a paid premium feature (new revenue line). | Feature-gated by subscription plan; per-hotel ownership checks; vendor cost billed per attempt; scrape can be stopped mid-run.
7 | Real-time updates (WebSocket + SSE) | Dashboards and availability update live — a new booking appears without refreshing the page. | The product feels modern and 'alive'; staff react to bookings instantly. | Connections require a verified login token; streams have lifetime caps so they cannot pile up.
8 | Date modification on checkout | Guests can change their search dates directly on the checkout page; prices refresh automatically. | Fewer abandoned checkouts — guests do not have to start over. | New dates/rates validated on the server, not trusted from the browser.
9 | Encrypted secrets vault | All hotel credentials (payment, WhatsApp, email, AI keys) stored AES-256 encrypted in Supabase Vault with a safe admin UI. | A database leak no longer exposes any hotel's payment or messaging accounts. | Secrets are write-only from the UI; never returned in plain text; never logged.
10 | Database-level tenant security (RLS) | The database itself refuses to return one hotel's data to another hotel, independent of application code. | A second, independent lock on customer data — a strong selling point for security-conscious chains. | Row Level Security policies on every tenant table, keyed to the verified login.
11 | CI/CD pipeline + automated test suite | Every code change automatically runs 277 tests (security, payments, roles, rate limits) plus a dependency vulnerability (CVE) scan before it can be merged. | Deploys become predictable; regressions are caught before customers see them. | Includes cross-tenant attack tests and coverage reporting.
12 | Bookable widget for hotel websites | An embeddable booking widget hotels place on their own websites, with chain-level booking support. | Hotels capture direct bookings (no OTA commission) — core product value. | Widget messages locked to the embedding site's verified origin; prices/availability always confirmed server-side.
13 | Dynamic pricing engine (hotelier-configured) | Hoteliers set rules (occupancy, day-of-week, lead-time) that adjust room prices automatically; a live preview shows the price on each calendar cell, and the rules drive the real booking charge. | A revenue-management feature (higher RevPAR) that competitors charge a premium for — a new selling point and revenue line. | Prices are server-computed with live occupancy; the client's price is verified within a tolerance; rules are role-gated and tenant-scoped.
14 | Abandoned-booking recovery | Automatically nudges guests who started but did not finish a booking, via WhatsApp and email, on an opt-in basis. | Recovers otherwise-lost bookings automatically — direct incremental revenue. | Runs on an hourly Redis-locked scheduler (one server only); per-hotel opt-in; senders never crash the booking flow; no PII logged.
15 | Loyalty points wallet + stay offers | Configurable earn/redeem rates, room-specific night-threshold offers, and a pre-booking nudge ('stay one more night to unlock'). | Deeper loyalty and longer stays — more direct, OTA-free revenue. | Redemption value is recomputed server-side from config (never trusts the client); role-gated; brand-isolated.
16 | Chain-wide upsell broadcast | A brand admin pushes one stay-upsell offer to every active property at once; each hotel gets its own row so the guest flow is unchanged. | Brand-level marketing in a single click across all properties. | Chain-admin only; isolated by chain_id; per-hotel rows share a broadcast id.
17 | Seasonal auto-apply promotions | Date-windowed deals that apply automatically with no coupon code (or as classic coupons), at hotel and chain level. | Easier campaigns and higher conversion (no coupon friction). | Discount always server-computed; usage incremented atomically; scoped to hotel or chain; the display banner is read-only.
18 | OTA / Booking.com-style booking widget | A professional, embeddable booking + search widget for hotel websites, with a floating calendar overlay and instant-load placeholders. | A polished direct-booking experience that rivals the OTAs — captures commission-free bookings. | Host-page-safe embed loader; hardened postMessage; iframe sandbox; the code-execution sink was removed (see S-50).
19 | Brand Console for multi-property owners | A collapsible brand workspace (overview, guest insights, brand promos, loyalty, upsell broadcast) for groups managing many hotels. | Makes the platform genuinely usable for hotel groups, not just single properties. | Gated by chain membership; every section validates the user's chain.
20 | Configurable rate plans & packages | Pure rate plans are separated from packages; packages gain an optional validity window and a 'you save' badge. | Clearer pricing setup for hoteliers and fewer mistakes. | Tenant-scoped; reuses the existing rate endpoints.
21 | Anti-automation booking token (HMAC) | A signed, short-lived token on the public booking path to deter scripted abuse (feature-flagged, off by default). | Protects the booking funnel from bots without slowing real guests. | HMAC-signed, time-bounded and rate-limited; enabled only when needed.
22 | Production observability (Sentry) | Error tracking with user context, a booking-funnel trail and payment-failure tracking. | We see and fix issues before customers report them — higher reliability. | No PII or secrets in events; scoped server-side.
23 | Engineering knowledge graph (graphify) | An AST-built map of the whole codebase (~4,800 nodes) that any engineer — or the AI assistant — consults before changing code. | Faster, safer onboarding and changes as the team grows; fewer regressions. | Local-only, no API cost; rebuilds automatically on commits.
EARLIER PLATFORM FEATURES (built across May – early June 2026)
24 | GST / tax engine | Configurable tax slabs (inclusive & exclusive), itemized tax breakdowns on every booking and invoice, and guest-facing price/tax disclosures. | Correct, compliant billing for Indian hotels — essential for trust and GST filing. | Tax is validated on save and computed server-side; guarded against NaN/zero-division.
25 | WhatsApp AI Agent | Per-hotel WhatsApp integration that sends booking confirmations and answers guests with AI, metered against subscription credits. | Guests get instant answers and confirmations on the channel they actually use. | Webhook payloads HMAC-verified; credits deducted per message; keys resolved from the encrypted Vault.
26 | Google Reviews AI Reply Studio | Per-hotel Google OAuth connect, fetch reviews, AI-drafted replies, and one-click posting back to the Google Business Profile. | Saves staff hours and improves the hotel's public reputation — a premium upsell. | Per-hotel OAuth tokens stored securely; scoped to the connected account.
27 | Google Hotel Ads integration | Feeds and UI to list a hotel's rates and availability on Google Hotel Ads. | A new demand channel for direct bookings. | Feature-gated by plan; per-hotel scoped.
28 | Multi-tenant email system | Custom email via SMTP or Brevo, with per-hotel sender, CC, signature and branded templates. | Confirmations and communications come from the hotel's own brand, not a generic system. | Per-hotel credentials encrypted; senders fail-safe so a mail error never breaks a booking.
29 | Super Admin platform console | A full operator console — KYC, commissions, payouts, support tickets, platform settings, MRR & plan breakdowns, system diagnostics, and secure impersonation with an exit banner and audit trail. | Lets us run Staybooker as a business: onboard, bill, support and oversee every hotel. | Superadmin-gated; impersonation tokens expire; every privileged action is audit-logged.
30 | Subscriptions & feature-gating | Subscription plans with a per-plan feature-allocation matrix, automatic feature sync, and premium locks across the product. | Turns features into packaged, sellable tiers — the core of the revenue model. | Plan checks enforced server-side; writes to subscription state are locked.
31 | Customizable role permissions | A per-hotel role-permission matrix (OWNER/MANAGER/STAFF and sub-roles) with a complete security audit trail. | Hotels control exactly what each employee can do — important for larger properties. | Permissions enforced on the backend, not just the menu; every change is logged.
32 | Configurable AI stack | AI agents on the Agno framework with per-hotel model choice (Llama, Google Gemini, DeepSeek), token limits, and a durable per-agent usage dashboard. | Right-sized AI cost and quality per hotel, with full visibility into spend. | Cheap model by default; token/tool-call limits; usage durably tracked in Postgres.
33 | Experiences & Activities upsell | Add-ons, services and amenities a guest can add at checkout (e.g. activities, transfers), managed by the hotel. | Higher average booking value — incremental revenue on every stay. | Prices validated server-side; tenant-scoped.
34 | Configurable cancellation & refund policies | Instant-vs-request cancellation modes (set by super admin) and room-level cancellation/refund overrides. | Hotels match the platform to their real policies — fewer disputes. | Mode enforced server-side; refunds run through the verified payment path.
35 | Booking source tracking & leads | Attribution of where each booking came from, AI-captured leads with filters, and CSV export of bookings and leads. | Hotels see which channels work and can follow up on leads — more direct bookings. | Tenant-scoped; exports limited to the hotel's own data.
36 | Embeddable widget suite | Multiple booking-widget layouts (Booking.com-style, STAAH-style, capsule, glassmorphism), theme-matched, with live per-date pricing and dual hotel + chain widgets. | Hotels add a professional, commission-free booking engine to their own website. | Host-page-safe loader; hardened postMessage; live prices confirmed server-side.
37 | Public presence & compliance | A premium landing page with smart subdomain routing, customizable hotel URL slugs, and the legal/compliance pages (refund, cookie, contact, Meta-verification). | A credible public face and the compliance pages required to operate and integrate. | Slug uniqueness validated; compliance pages public by design.

## 4. Work In Progress
What Is Being Worked On Right Now
Critical items in progress — one person cannot do these in parallel, which is why a team is needed
ID | Task | Why It Matters | Status | Risk If Delayed
P-01 | Razorpay payment failure recovery (money deducted but booking not created) | A Razorpay refund endpoint, idempotency keys and webhook signature verification are already built. The remaining pieces are the FULLY-AUTOMATIC refund flow and a daily reconciliation job (matching the Razorpay ledger to our bookings). | In Progress (foundations done) | Guests' money stays stuck and refunds must be done manually. Angry guests, chargebacks, Razorpay disputes.
P-02 | Load testing — what happens when 100+ users book at the same time | A load-test harness and scale documentation (SCALE_TUNING.md) already exist, and database row-locks protect against double-selling a room. The remaining work is running load tests at realistic scale and tuning the connection pool / auto-scaling from the results. | In Progress (harness ready) | The site goes down during peak season or a viral campaign — losses on exactly the highest-revenue days.
P-03 | Frontend page-by-page error audit (errors + edge cases on every page) | Real progress since the last report: the blank-screen (createContext) crash is fixed (S-48), instant-load placeholders and skeleton price cells are in, and the booking-widget pages were hardened (S-50, plus the earlier S-34/S-36/S-37). The hotelier dashboard pages are the remaining batch. | In Progress | White screens and stuck buttons in front of guests = dropped bookings and brand damage.
P-04 | DDoS / abuse protection layer (WAF) | The IP-spoofing hole is fixed (S-40), key routes are rate-limited (S-42), and a signed anti-automation booking token (HMAC) now guards the booking path. The remaining piece is an edge layer (Cloudflare/WAF) to absorb large-scale attacks before they reach our servers. | In Progress | Large fake-traffic attacks are inexpensive to launch and could make the site unavailable on important days.
P-05 | Database migration discipline (Alembic in the deploy process) | Alembic is set up (divergent heads merged, migrations made idempotent), but several newer features still create tables via create_all/init_db at startup. The remaining work is to bring every schema change under one consistent Alembic process. | In Progress (Alembic exists) | As data grows, queries get slow → the whole app gets slow.
P-06 | Remaining medium-severity audit findings | Several have been closed since: the widget code-execution sink was removed (S-50), chat postMessage origin locked, and loyalty read endpoints role-gated (S-53). Items still open: the login-token cache window (~10 min), the unsigned OAuth state parameter, and stale analytics cache invalidation. | In Progress | Each one is a small gap today; closing them before scale keeps the risk small.
RECENTLY COMPLETED (graduated out of 'in progress' since the last report)
Revenue Engine shipped (dynamic pricing, abandoned-booking recovery, loyalty wallet & upsell hub) - PR #80; chain features, package improvements & seasonal promotions - PR #88; the recovery scheduler and the booking create/cancel 500 crashes - PR #83; the Cloudflare blank-screen crash - PR #82; the broken-deploy and missing-migration fixes - PR #84/#85; production observability (Sentry) and the engineering knowledge graph - PR #59/#86. All are reflected in Sheets 2 and 3.

## 5. Future Risks
Future Possible Errors — Real Scenarios
These problems have not happened yet, but they WILL come as the business grows. 'Protection Already In Place' = what has already been implemented.
ID | Scenario (Example) | What Can Happen | Why It Will Happen | Protection Already In Place | What Still Needs To Be Built | Severity | Which Developer Owns This
F-01 | 100 people press 'Book Now' at the same time (festival sale / ad campaign) | The same room gets sold to 2-3 guests (overbooking), or the server times out and everyone sees errors | The database connection pool is limited; there is a race-condition window; everyone competes for a lock on the same inventory row | Row-level database locks on inventory; Redis idempotency; pagination everywhere; composite index on the hottest availability query | Load testing, a queueing system, connection pool tuning, auto-scaling rules | Critical | Backend + Database
F-02 | A guest enters card details and pays, but the network cuts out — Razorpay verification fails and the booking is cancelled. The guest pays again = DOUBLE PAYMENT | The guest is charged twice; refunds must be processed manually; chargebacks and Razorpay disputes follow | A payment passes through 3 systems (browser → Razorpay → our server) — any link can break at any moment | Idempotency keys (the same order is never processed twice); webhook signature verification; status guard (a CONFIRMED booking is never re-processed) | An automatic refund flow, a daily reconciliation job (matching the Razorpay ledger against our bookings), and a 'payment pending' recovery screen for the guest | Critical | Backend
F-03 | A hotel's data grows to several GBs (2-3 years of bookings and analytics) | The dashboard takes 15-20 seconds to open; reports time out; the browser freezes rendering thousands of rows | Current queries are fast on small data; large data needs an index/partition strategy; the frontend has no virtualization | Pagination on all lists; Redis caching on heavy aggregations; key database indexes | Data archiving (old bookings moved to separate tables), table partitioning, virtual scrolling in the frontend, pre-computed reports | High | Database + Frontend
F-04 | The site receives a flood of fake traffic (a DDoS attack) on the booking engine | The site goes down on a peak day; real guests cannot book; the hosting bill rises sharply | Public endpoints are anonymous and attract bots; large attacks must be absorbed before they reach our servers | Redis-backed rate limiting; spoof-proof client IP detection (trusted proxy); per-hotel AI quotas; per-route caps on password change/uploads/reports; limits on streaming connection lifetimes; PLUS a signed anti-automation booking token (HMAC) on the booking path. | A Cloudflare/WAF edge layer, bot detection (CAPTCHA on abuse), infrastructure alerts | Critical | Backend + DevOps
F-05 | Someone deliberately probes new endpoints for data-isolation gaps (Hotel A accessing Hotel B's data) | A single tenant-isolation bug would mean a data breach — loss of customer trust and possible DPDP penalties | Every new feature adds new endpoints to protect; right now only one person reviews everything | Row Level Security at the database level (a second lock); 130+ security tests; audit-driven engineering rules; cross-tenant attack tests | Regular penetration testing, a security review on every code change (Tech Lead), a bug bounty program later | Critical | Backend + Tech Lead
F-06 | A guest on a slow 3G network presses the button twice | Two bookings get created, and two payment attempts are made | Submit-locks and loading states are not yet consistent on every frontend page | Backend idempotency ensures the same payment is never processed twice; promo/loyalty redemption now takes row locks (SELECT FOR UPDATE) so a balance cannot be double-spent under concurrent clicks (S-51). | Double-submit guards on every form, optimistic UI, retry logic with backoff, offline detection | High | Frontend
F-07 | Razorpay, Supabase or Redis goes down | The entire booking flow fails and the guest has no idea what happened | We depend on third-party services — their downtime is our downtime | A Redis failure does not block the booking flow (graceful fallback); missing payment keys show a clear maintenance message | A status page, circuit breakers, queue-and-retry for emails/sync, a multi-region plan | High | Backend + DevOps
F-08 | Someone spams the public AI chatbot with a script | The AI bill runs into lakhs; legitimate hotels' quotas get exhausted | The endpoint is anonymous, and LLM tokens cost real money | Per-hotel daily quotas; cheap model by default; tool-call limits; response caching; usage tracking now durably stored in Postgres so it survives a Redis outage (PR #63). | Anomaly alerts (bill spikes), CAPTCHA on abuse patterns, stronger per-IP + fingerprint limits | High | Backend
F-09 | 50-100 hotels onboard (sales success!) | Database connections run out (Supabase limit) and all tenants slow down at once | The pool-size × workers × replicas math is currently tuned for a single instance | Environment-driven pool sizing; per-worker pools documented (SCALE_TUNING.md) | A connection pooler (PgBouncer), a horizontal scaling plan, per-tenant monitoring | High | Database + DevOps
F-10 | A hotelier uploads a wrong or unsafe CSV/photo file | Server crash, or malware stored and served from our domain | An upload feature is always an attack surface | Magic-byte validation, server-side content-type detection, size caps, randomized filenames | Virus scanning, isolated image processing, serving files via CDN | Medium | Backend
F-11 | The booking page loads slowly from Google (3-4 seconds) | Guests bounce — research shows every extra second of load time cuts conversion by ~7%. Direct revenue loss every single day | Bundle size, images and render-blocking scripts have not been optimized yet | Vite build optimisation at a basic level; instant-load placeholders and skeleton price cells added on the booking and widget pages so the first paint is never empty (S-48). | Code splitting, image optimization, lazy loading, Core Web Vitals monitoring — THIS IS FRONTEND ENGINEERING, NOT UI DESIGN | High | Frontend
F-12 | The same record is open in 2 tabs and edited in both | The last save wins — the first edit is silently lost | There is no optimistic concurrency control yet | Critical paths (inventory) already use database locks | Version checks on edits, conflict warnings in the UI | Medium | Frontend + Backend
F-13 | Backups have never been restore-tested, and one day the database gets corrupted | Losing every hotel's data would be a loss the business could not recover from | Supabase keeps backups, but a restore drill has never been performed | Supabase automated backups (platform-level) | Quarterly restore drills, point-in-time recovery setup, a disaster recovery runbook | Critical | Database
MORE SCENARIOS AS WE SCALE — many hotels and their guests all share the same servers
F-14 | One busy hotel's traffic or heavy reports slow down every other hotel ('noisy neighbour') | All hotels share the same servers and database; one hotel running a huge report or a sale can starve the rest | Shared multi-tenant infrastructure with finite CPU, connections and memory | Pagination and row caps everywhere; per-hotel AI quotas; Redis caching; env-driven pools | Per-tenant rate/usage limits, query budgets, and isolating heavy reports onto background workers/replicas | High | Backend + Database + DevOps
F-15 | A popular cached page expires and hundreds of requests hit the database at once (cache stampede) | A sudden database spike can slow or stall the site exactly when traffic is highest | When one cache key expires under heavy load, every request rebuilds it simultaneously | Redis caching with an in-memory fallback layer | Stale-while-revalidate, request coalescing (single-flight) and jittered cache TTLs | High | Backend
F-16 | Two staff or two guests update the same inventory at the same moment and the database deadlocks | Some requests fail with errors during the busiest booking moments | Concurrent writes to the same rows across many hotels can deadlock in Postgres | Row-level locks (SELECT FOR UPDATE) on inventory and redemption | Consistent lock ordering, retry-on-deadlock, and shorter transactions | Medium | Database
F-17 | Email/WhatsApp providers throttle or reject our messages and guests stop getting confirmations | Guests miss confirmations and OTAs aren't synced — more support calls, double bookings | Brevo/Meta enforce sending limits and deliverability rules that tighten as volume grows | Senders are fail-safe (never crash the booking); per-hotel credentials | A queue with retry/back-off, deliverability monitoring, and provider fail-over | High | Backend
F-18 | A hotel's WhatsApp/Meta token expires or a template is rejected and notifications silently stop | That hotel's WhatsApp confirmations quietly stop working | Meta tokens expire and message templates need approval; both change over time | Per-hotel config; webhook signature verification | Token-expiry alerts, template-status checks, and a clear 'reconnect' prompt | Medium | Backend
F-19 | Google review/Business-Profile OAuth tokens expire and the review features silently stop | The reviews studio stops fetching or posting for that hotel | OAuth refresh tokens can be revoked or expire | Per-hotel OAuth tokens stored securely | Automatic token refresh, expiry alerts, and a guided reconnect flow | Medium | Backend
F-20 | A Razorpay webhook is replayed or arrives out of order and a payment is processed twice | A guest could be double-charged or a booking double-confirmed | Webhooks can be retried, duplicated or delayed by the network | Idempotency keys; webhook signature verification; status guard on confirmed bookings | Event de-duplication by event id and an ordered, idempotent webhook processor | High | Backend
F-21 | Hotels in different regions hit date/timezone bugs (check-in/out or reports off by a day) | Wrong nights charged, wrong availability, or reports that don't match the hotel's day | Dates are computed in multiple layers; timezones differ per hotel | Server-side price and date validation | A single, explicit timezone strategy per hotel and timezone tests | Medium | Backend + Frontend
F-22 | Stored data (guest images, invoices, backups) grows unbounded as hotels and stays pile up | Storage costs climb and large objects slow pages and backups | Every booking and hotel adds images and documents that are never cleaned up | Randomized filenames; size caps on uploads | Object storage on a CDN, lifecycle/archival rules, and an image-processing pipeline | Medium | Database + DevOps
F-23 | A bug loop or an attack floods the logs/monitoring and the observability bill explodes | Monitoring costs spike and real errors get buried in noise | High traffic plus an error loop can generate enormous log volume | Sentry sampling reduced in production; no PII in logs | Log rate-limiting, error de-duplication, and budget alerts on observability spend | Medium | Backend + DevOps
F-24 | A new hotel onboards with a bad bulk import (rooms/rates/bookings) and pages break | The new hotel's dashboard or booking page errors out on day one | Imported data may have missing fields, wrong types or duplicates | Server-side validation on the main write paths | A validated import pipeline with a dry-run preview and clear error reporting | Medium | Backend + Frontend
F-25 | An AI provider has an outage or deprecates a model and the chatbots/agents stop or misbehave | Guest and hotelier AI features go down or change behaviour suddenly | We depend on third-party LLMs whose availability and models change | Cheap model by default; per-hotel model selection; usage tracking | Multi-provider fail-over, model pinning, and a graceful 'AI unavailable' fallback | Medium | Backend
F-26 | A guest exercises their DPDP/GDPR right to be forgotten and we must delete their data correctly | A mishandled deletion is a compliance violation; an over-broad one corrupts records | Privacy law requires verifiable deletion across many tables and many hotels | Per-hotel data isolation; encrypted PII | A documented data-deletion/anonymisation workflow and an audit record of each request | Medium | Backend + Database
F-27 | A vendor key leaks and must be rotated across all hotels without downtime | A compromised key must be replaced fast, for every affected hotel, with no outage | Keys can leak through logs, laptops or third parties; we hold many per hotel | All secrets encrypted in the Vault; never returned in plain text; masked in APIs | A documented key-rotation runbook and per-hotel re-key tooling | High | Backend + Tech Lead
A REALISTIC CLOSING NOTE — WHY THIS WORK NEVER FULLY 'ENDS' (AND WHY A TEAM IS NEEDED)
In software development, nothing is a permanent solution. The product is healthy today, but it lives in a moving world:
• New updates will keep coming — and any update can itself arrive with new bugs.
• New features must keep being added to Staybooker to compete — as competitors release features in their software, we have to as well, and every new feature is new surface area where issues can appear.
• Third-party APIs change — payment gateways like Razorpay / JioPay update their APIs; if our system does not capture and adapt to those changes in time, errors or bugs can appear.
• Infrastructure can be strained — our cloud host (Railway) can be overloaded during traffic spikes.
• Real usage is unpredictable — the scenarios in this sheet are informed PREDICTIONS, not certainties. For example: even with 10 hotels, each taking ~15-20 bookings a day (~200 bookings daily), plus 50-100 visitors/guests taking actions on the site at any moment, we cannot predict every combination of what they will do.
So when something does break, there must be a team in place to catch and resolve it BEFORE it grows into a high-priority, customer-facing incident. That is the real reason for the hiring in Sheet 6 — not because the product is broken, but because keeping it healthy is continuous work.

## 6. Team & Hiring
Team & Hiring — Decision Support
The product is stable today and data is safe. This sheet maps which role owns which part as the business grows.
WHERE THE PRODUCT STANDS TODAY
Area | Current Status
Product stability | Stable for current hoteliers — bookings, payments, dashboards and integrations are working. 58 issues have been found and fixed proactively, and 277 automated tests now run on every code change.
Data safety | Safe — all credentials are encrypted (AES-256 vault), every hotel's data is isolated at both the application and the database level, and payment amounts are always verified on the server.
Hotelier experience | No major issues expected at today's scale. The public booking flow has been hardened (error recovery, date validation, double-payment protection).
Why hiring, then | Growth. As hotels onboard, data will reach GBs and traffic will multiply. Each layer of the product — database, backend, frontend — then needs a dedicated owner so quality stays exactly where it is today.
HOW DATA TRAVELS THROUGH THE PRODUCT — AND WHO OWNS EACH STEP
Step in the Data Journey | Owner | Exact Job
1. Data lives in the database (bookings, rates, guests) | Database Dev | Makes sure data comes OUT of the database smoothly — right indexes, fast queries, clean schema, reliable backups, per-hotel isolation. When data reaches GBs: partitioning and archiving so queries stay fast. Builds to the Tech Lead's design and reports progress to him.
2. Backend picks up the data and serves it through APIs | Backend Dev | Connects the backend APIs to the database properly — booking logic, payment processing, security checks. When data reaches GBs: sends it in CHUNKS (pagination, batching, caching) so the server never tries to load everything at once. Builds to the Tech Lead's design and reports progress to him.
3. Frontend calls those APIs and shows the data on screen | Frontend Dev | Connects the React + TypeScript frontend to the backend APIs and makes sure the data arrives and displays correctly — loading states, error handling, payment screens. When data reaches GBs: loads it smoothly on screen (paged lists, lazy loading) so pages stay fast for the hotelier and the guest. Builds to the Tech Lead's design and reports progress to him.
4. Someone decides WHAT to build, HOW to build it, reviews it, and signs off before release | Tech Lead | TECH LEAD — the decision-maker and the final gate. Requirements from the product manager / stakeholders come to him; he designs the architecture, breaks it into tasks for each developer, reviews every change, and by his experience decides whether it is safe to ship to production. The developers below build to his direction and report to him. He is accountable for every software update, every bug and every crash.
ROLE SUMMARY — WITH EXAMPLES FROM OUR OWN PROJECT
Role | In One Line | Examples of This Work Already Done in the Product
Tech Lead | The single person accountable for the whole software — every update, bug and crash. He decides what gets built, when and how it is coded, reviews and approves every change before it can reach production, and the developers execute his plan and report to him. | Turns feature requests from the product manager / stakeholders into an architecture and a set of tasks; assigns each task to the right developer; reviews ALL code and, by experience, decides what is safe to ship to production; owns the engineering rules, the review checklist and the CI/CD gate; carries responsibility when anything breaks. (In this project: set the fix order across 70+ issues money-first, wrote the rules the team follows, and stood up the test/CI gate.)
Backend Dev | Owns backend APIs and their connection to the database — payments, booking logic, security, performance. Builds what the Tech Lead designs — the 'what' and 'why' come from him; reports progress back to him. | Server-side payment verification (amount can never be tampered from the browser); double-payment protection when a guest's network fails; pagination on heavy endpoints; rate limits against abuse.
Frontend Dev | Owns the React + TypeScript screens and their connection to backend APIs — correct data display, smooth experience. Builds the screens to the Tech Lead's design and direction; reports to him. | Error + retry handling on the booking pages (a network blip no longer shows a blank page); date validation before search; live-updating dashboards; checkout flow with loyalty points calculated safely via the API.
Database Dev | Owns the database — speed, schema, backups, and the guarantee that data flows out smoothly at any size. Implements the data design the Tech Lead approves; reports to him. | Database-level isolation between hotels (Row Level Security); composite indexes on the busiest availability queries; encrypted credential storage; chain-level loyalty data design.
SUGGESTED HIRING ORDER
Priority | Role | Why This Order | Focus in the First 90 Days
1 | Backend Dev | The next milestones are payment-recovery automation and handling high booking traffic — both backend work. | Automatic refund + payment reconciliation; load testing the booking path; finishing the abuse-protection layer.
2 | Frontend Dev | The hotelier dashboard pages are next in line for the same error-handling polish the public booking pages already received. | API integration hardening on every dashboard page; page speed optimisation; error monitoring.
3 | Database Dev | Becomes essential as data approaches GB scale; can begin part-time and grow with the data. | Migration process; backup restore drills; query and index plan for large hotels; capacity plan for onboarding more hotels.
With the first hire | Tech Lead | Direction and review from day one. He is the owner of quality and safety — nothing reaches production without his approval — so the work of every other hire stays consistent and safe. Should be a senior, hands-on engineer who can also code. | Set the technical roadmap and architecture; define the code-review and release process; assign and supervise all developer tasks; own incident response.
A NOTE FOR STAKEHOLDERS (why this ask, framed plainly)
This is not a request to fix something broken — the product works and customer data is safe today. It is a request to PROTECT what has been built and to DE-RISK growth. Up to now one person has carried database, backend and frontend together. That is fine at the current size, but every new hotel multiplies the data, the traffic and the number of places a single quiet bug could cause a slow page or an outage. Each role below removes a specific, named risk to revenue and reputation. Hiring in the order shown means we always add the person who removes the biggest risk next — never headcount for its own sake.
WHAT EACH HIRE RETURNS (in business terms)
Role | The risk it removes | What the business gets back | If we keep delaying
Backend Dev | Stuck payments, slow APIs under load, runaway costs, a crash on a peak day. | Money never gets stuck (auto-refund + reconciliation); the booking path stays fast when 100 people book at once; AI and server bills stay predictable. | A peak-day outage or a stuck-payment incident on the highest-revenue day — exactly when it hurts most.
Frontend Dev | Blank/white screens, double bookings, slow pages that make guests leave. | Every page recovers from a network blip with a Retry; no duplicate bookings; pages load in under ~2s, which directly lifts conversion. | Lost bookings every day to slow or broken pages — a silent, daily revenue leak that is hard to even notice.
Database Dev | Dashboards crawling once data reaches GBs; a backup that has never been test-restored. | Queries stay in milliseconds at any data size (indexes, partitioning, archiving); backups are proven to actually restore. | The product feels slower for every hotel as it succeeds — and an un-tested backup is a bet the business cannot afford to lose.
Tech Lead | No single owner of quality; code reaching production with no experienced second pair of eyes; no clear accountability when something breaks. | One accountable owner for the entire software — every update, bug and crash. He designs each feature, assigns the tasks, and personally approves what ships, so quality and safety do not depend on luck. | Developers build in different directions, reviews get skipped, and a single silent bug (see the Silent Bugs sheet) can reach production unchecked.
HOW THE TEAM WORKS — THE CHAIN OF COMMAND
Step | Who | What happens
1 | Product Manager / Stakeholders | Decide WHAT the business needs — new features, priorities, customer requests — and hand them to the Tech Lead.
2 | Tech Lead | Architects the design and the approach, decides HOW and WHEN it is built, and breaks it into specific tasks for each developer.
3 | Backend / Frontend / Database Developers | Build their assigned tasks to the Tech Lead's design. They focus on writing the code; the 'what' and 'why' come from the Tech Lead.
4 | Tech Lead (review gate) | Reviews every change. By his experience he decides whether it is safe to go to production — nothing ships without his approval.
5 | Tech Lead (accountability) | Owns the result: any update, bug or crash is his responsibility. The developers report to him; he reports to the business.

## 7. Engineering Plan by Role
Engineering Plan by Role — What Each Developer Does, Day to Day
The concrete, ongoing engineering behind 'why a team'. None of these roles is graphic/visual design — this is software engineering.
HOW THE PIECES CONNECT: The Frontend (TypeScript / React) calls the Backend APIs → the Backend APIs talk to the Database. Each developer owns one link in that chain and writes the CODE for it. The Tech Lead decides what is built and reviews it all.
FRONTEND DEVELOPER
Writes the TypeScript / React code that runs in the guest's and hotelier's browser and TALKS TO THE BACKEND APIs. This is engineering — typed code, data handling, performance — not visual design. Builds to the Tech Lead's design and reports to him.
Ongoing job | What the work actually is (day to day) | Why it matters to the business | What it prevents
Call the backend APIs (TypeScript) | Write the typed TypeScript code that calls each backend endpoint: send the correct request, read the response, and keep the frontend's data types matching the backend's contract so data never arrives in the wrong shape. | The screens show exactly the data the backend returns — bookings, rates, availability — correctly and reliably. | Broken pages, wrong data on screen, and type mismatches that crash a component.
Manage state & data flow | Decide how fetched data moves through the app — caching with React Query, re-fetching on focus, and invalidating the cache after a booking/edit so the screen updates. | Hoteliers and guests always see fresh, correct data without manual refreshes. | Stale screens (e.g. a sold room still showing as available).
Loading, error & retry handling | Give every screen a proper 'loading', 'failed' (with a Retry button) and 'empty' state, and tolerate slow or partial API responses. | A slow network or a failed API call never leaves the guest staring at a blank white page mid-booking. | Blank screens and stuck buttons that make guests abandon a booking.
Performance engineering | Code-splitting, lazy-loading, bundle-size trimming, image optimisation and virtual scrolling for big lists; measure and fix slow renders (Core Web Vitals). (Build/runtime engineering, not graphic design.) | Pages load in ~1-2 seconds even for large hotels — and faster pages convert more guests. | Slow pages that lose bookings, and browsers freezing on thousands of rows.
Concurrency & input safety | Disable buttons on submit, debounce rapid clicks, and validate inputs in the browser before they reach the API. | No accidental duplicate bookings or double payments on slow networks. | Two bookings / two charges from one impatient double-click.
Real-time UI | Wire the live WebSocket / SSE streams from the backend into the screens so a new booking appears instantly. | The product feels live; staff react to bookings without refreshing. | Missed or stale information on the dashboard.
BACKEND DEVELOPER
Writes the API code that the frontend calls, and that in turn TALKS TO THE DATABASE. Owns booking logic, payments, security, speed and cost. Builds to the Tech Lead's design and reports to him.
Ongoing job | What the work actually is (day to day) | Why it matters to the business | What it prevents
Design & build the APIs | Build the endpoints the frontend calls: validate the request, run the business rules, and return the correct JSON shape (the 'contract' the frontend depends on). | Every screen has a reliable, correct API behind it. | Broken or inconsistent responses that break the frontend.
Talk to the database correctly | Write the queries each API uses to read/write data — always scoped to the caller's hotel, batched (no N+1), and paginated. | Data is correct, isolated per hotel, and fast to fetch. | Cross-tenant leaks, slow queries, and out-of-memory crashes on big hotels.
API optimisation | Measure each endpoint's response time, cache hot reads in Redis, and push slow work (emails, channel sync) into background jobs. | Responses stay in milliseconds and the server bill stays low — speed is revenue. | Timeouts and a database overloaded by repeated heavy queries.
Payments & third-party integrations | Razorpay / JioPay, WhatsApp, email: verify signatures, handle webhooks and retries, and ADAPT when a provider changes its API. | Money is handled correctly and integrations keep working as vendors change. | Stuck payments, double charges, and notifications silently breaking.
Security & continuous bug-hunting | Add the role gate + tenant filter + server-side amount/id verification to every route; read every change for the silent failure modes in Sheet 8. | New features ship without opening data-isolation, tampering or crash holes. | Breaches, price/role tampering, and silent server crashes.
Cost control & observability | Cap LLM tokens, enforce per-hotel quotas, bound rows/work; emit structured logs (no PII) and error alerts. | Predictable AI/infra cost and problems seen before customers complain. | Surprise bills and outages discovered only via angry hoteliers.
DATABASE DEVELOPER
Owns the database the backend talks to — speed, schema, safety and the guarantee that data flows out smoothly at any size. Implements the data design the Tech Lead approves and reports to him.
Ongoing job | What the work actually is (day to day) | Why it matters to the business | What it prevents
Schema & migrations | Design the tables and run every schema/index change through one safe, repeatable process (Alembic) instead of ad-hoc startup scripts. | Production never silently misses an index or a column. | Half-applied schemas and 'works locally, crashes in production' bugs.
Indexing & query plans | Add and tune indexes on the hottest columns (hotel_id, dates, status); read query plans and fix the slow ones. | The busiest queries stay in milliseconds as data grows. | Searches and reports getting slower for everyone over time.
Partitioning & archiving | Move old bookings/analytics to separate tables; partition large tables by date/hotel. | Day-to-day queries only touch small, recent data — so they stay fast. | Dashboards taking 15-20s to open once a hotel has years of data.
Connection pooling & capacity | Add a pooler (PgBouncer) and tune pool-size x workers x replicas against the Supabase limit; plan capacity for more hotels. | 50-100 hotels can onboard without the database running out of connections. | All tenants slowing down at once when connections run out.
Backups & restore drills | Run real restore drills, set up point-in-time recovery, and write a disaster-recovery runbook. | Backups are proven to work before we ever need them. | Discovering a backup is unusable on the worst possible day.
Isolation on every change | Review every new table for Row Level Security and per-hotel isolation. | The database itself keeps refusing to mix one hotel's data with another's. | A schema change quietly opening a cross-tenant leak.
TECH LEAD
Accountable for the WHOLE software — every update, bug and crash. Converts product/stakeholder requirements into an architecture and tasks, assigns them, reviews every change, and decides what is safe to ship. The three developers above execute his direction and report to him.
Ongoing job | What the work actually is (day to day) | Why it matters to the business | What it prevents
Architecture & decisions | Turn each feature request into a design and an approach; decide what is built, in what order, and how it is coded. | Effort goes to the highest-value work, built the right way the first time. | Rework, wrong-priority work, and inconsistent code.
Assign & supervise tasks | Break the work into specific tasks for the backend, frontend and database developers and track their progress. | Everyone knows exactly what to build; nothing falls through the cracks. | Developers building in different directions.
Review gate (production sign-off) | Read every change. By experience, decide whether it is safe to go to production — nothing ships without his approval. | The single most effective catch for the silent bugs in Sheet 8. | A quiet bug reaching production with no experienced second pair of eyes.
Release & incident response | Own the CI/CD pipeline and the deploy process, and lead the response when something breaks. | Deploys are predictable and incidents are handled calmly. | Risky deploys and slow, chaotic recovery.
Accountability & security posture | Carry responsibility for every update, bug and crash; schedule pen-tests and drive audit follow-ups. | One clear owner of quality and safety as the product grows. | Diffused responsibility and security drifting as the surface grows.

## 8. Silent Bugs & Stability
Silent Bugs & Server Stability — The Quiet Risks That Crash a Server
The dangerous bugs are the ones with NO error on screen — the server slowly leaks memory, stalls, or crashes while everything looks fine. Below is that class of risk, what already protects us, and the ongoing work that keeps it safe. Most of these we have already met and fixed once (the S-xx references point to Sheet 2).
Silent risk (plain language) | How it quietly hurts the server | Already protected | Continuous work needed | Owner
Swallowed errors (a background job fails but no one is told) | Confirmation emails and channel-sync silently skip — guests get nothing, OTAs double-book — with zero error shown. We hit exactly this (S-12). | Background-task pattern fixed; engineering rule bans bare 'except: pass'; errors must be logged or re-raised. | Read every new background job in code review; alert on task failures. | Backend + Tech Lead
Query returns more rows than expected (cardinality crash) | An endpoint that assumes one row gets several and throws a 500 only for certain data — invisible until that exact data appears. We hit exactly this in the loyalty check (S-46). | Rule to use .first() not scalar_one_or_none() where multiple rows are possible; tests around it. | Review every new query for this pattern; add tests for multi-row cases. | Backend
Unbounded query (no limit) loads everything into memory | A big hotel's list endpoint tries to load 100k rows and the server runs out of memory and crashes (S-13, S-43). | Pagination (limit + offset) is mandatory on list endpoints, with hard caps; indexes on hot columns. | Enforce a limit on EVERY new list endpoint; reject unbounded date ranges. | Backend + Database
'Fail-open' safety check (limit turns OFF when Redis is down) | During a Redis blip the AI-spend limit silently passes everything — runaway cost or overload until someone notices (S-39, S-44). | Quotas now 'fail closed'; an in-process cap takes over; Redis self-heals after a 30s back-off. | Audit every new limit/lock to confirm it fails closed, not open. | Backend
N+1 queries (one page quietly fires hundreds of DB calls) | Looks fine on small data; as data grows the database is hammered and every page slows for everyone. | Batch loading with selectinload / single GROUP BY queries. | Review new endpoints for query count; watch slow-query logs. | Backend + Database
Connection-pool exhaustion under load | At 100 simultaneous bookings the pool empties and every request stalls — the whole site appears down (F-01, F-09). | Env-driven pool sizing; documented pool math (SCALE_TUNING.md); row-level locks on inventory. | Load testing, a connection pooler (PgBouncer), auto-scaling rules. | Backend + Database + DevOps
Stale cache serves wrong data | Cache isn't cleared after a booking/cancellation, so a sold room shows as 'available' and gets double-sold (S-21). | Cache invalidation + a version counter bumped after every booking/cancellation. | Invalidation discipline on every new cached path. | Backend
Uncaught frontend error blanks the whole page | One failed fetch (or an unsafe bundling change) turns the entire screen white mid-booking — the guest just leaves. We hit this twice and fixed both (S-36, S-48). | Error + Retry UI on the booking pages; add-ons load separately so their failure can't blank the page. | Same hardening on every dashboard page; a top-level error boundary. | Frontend
Resource leak (threads / streams pile up) | Long-lived connections or threads are never released; the server slowly bloats and dies hours later — no obvious cause. | Streaming connections have lifetime caps; web search runs in a thread with an 8s hard timeout. | Monitor memory/thread counts; cap every new long-lived resource. | Backend
Unvalidated input / bad settings saved | Negative tax, inverted slabs or a divide-by-zero produce wrong bills for every guest — silently, until accounts notice (S-41). | Server-side validation rejects bad values; calculators guarded against NaN. | Validate every new settings/input form server-side, not just in the browser. | Backend + Frontend
WHY THE WHOLE SOFTWARE WILL NOT GO BLANK (the safety net)
• Layered fallbacks: if Redis crashes, the app transparently falls back to an in-memory cache — it never crashes because of Redis.
• No blank screens: a failed data fetch shows a clear message with a Retry button; optional pieces (add-ons) load separately so one failure can't take down the page.
• Fail closed on money & security, fail soft on the screen: anything touching payment, roles or another hotel's data DENIES on doubt; anything touching the display keeps working in a reduced mode.
• Tested on every change: 277 automated tests (including Redis-failover and cross-tenant attack tests) run before any code can merge.
• The 'safer side' principle the CEO asked for: when in doubt we choose the cautious behaviour — reject the risky action, keep the guest's screen usable, and log it for a human to review.

## 9. Scaling to Large Data
Scaling to Large Data — Database → Backend → Browser in Milliseconds
When a hotel has 2–3 years of bookings (GBs of data), the page must still load in milliseconds and must never freeze or go blank. This is the speed 'budget' for the journey of one request, what already holds it, and what we build to keep holding it as data grows.
Stage of the journey | What happens here | Speed target | In place today | To build for GB-scale | Owner
1. Database | Find and return the right rows (bookings, rates, guests) for this hotel only. | < 50 ms / query | Indexes on hot columns; Row Level Security; pagination; composite index on the busiest availability query. | Table partitioning by date/hotel; archive old bookings; read replicas for reports. | Database
2. Backend API | Shape the rows into a clean API response, applying security and business rules. | < 100 ms | Redis caching on heavy aggregations; mandatory pagination; lazy heavy imports; batched queries (no N+1). | Pre-computed report tables; response compression; background pre-warming of common queries. | Backend
3. Network & cache | Carry the response to the browser, reusing cached copies where safe. | < 100 ms (cache hit ~0) | React Query caches GETs for 5 min; public reads cached in Redis. | Cloudflare edge caching; ETags/conditional requests so unchanged data isn't re-sent. | Backend + Frontend
4. Browser render | Draw the data on screen — lists, charts, the booking calendar. | < 1 s, no freeze | Paged lists; loading + error + Retry states on the booking pages. | Virtual scrolling for huge lists; code-splitting & lazy loading; skeleton loaders. | Frontend
TOTAL (guest experience) | From click to a fully usable screen. | Well under ~2 s | Holds comfortably at today's data sizes. | Stays under ~2 s at GB-scale once the above are in place. | All three roles
AND IT STAYS ON THE SAFER SIDE AT SCALE
• Even when data is huge, the app never tries to load everything at once — the database sends rows in pages, the backend serves them in chunks, and the frontend draws only what's on screen.
• If any stage is slow or fails, the guest sees a Retry — never a frozen tab or a white page.
• Money and security checks never get 'skipped to go faster': they stay strict (fail closed) no matter the load. Only the display degrades gracefully, never the safety.
• Costs stay bounded as data grows: capped result sizes, caching, and per-hotel quotas mean more data does not mean a runaway bill.