## Issue Tracker
🏨 Hotel Booking Engine — Issue & Error Tracker
Status: 5 of 34 fixed already (incl. the critical AI-assistant restore) • 29 logged as a proactive hardening roadmap — latent risks that surface under live guest load, not current outages. Backend tests green (253 passed); CI/CD strengthened.
ID | Phase | Category | Error / Issue | Description | Root Cause | Recommended Fix | Priority | Status | Assigned To | Reported Date | Target Date | Resolved Date | Resolution Notes | Time to Fix (days) | Remarks
BE-001 | Pre-Development | AI / Cost Governance | Define a per-hotel AI spend budget & billing model | Token usage is already recorded per hotel/day (ai_usage.py -> Redis ai_tokens:{hotel}:{date}); what's missing is a budget ceiling, alert threshold and a bill pass-through decision. ⏱ When it surfaces: As paid AI usage grows across many live hotels. | Cost governance was not defined as a requirement up front. | Set a monthly AI ceiling per plan tier; alert on the existing counters; decide absorbed vs passed-through cost. | High | Open | Tech Lead / Founder | 10/06/2026 |  |  |  |  | Protects margin: prevents a slow, invisible LLM-cost creep from showing up only on the monthly invoice.
BE-002 | Pre-Development | Infrastructure / Trust | Pin the trusted reverse-proxy hop for client IP | Rate limiting reads the first X-Forwarded-For value (limiter.py). Behind most proxies the client can set this header, so IP-based limits can be diluted. ⏱ When it surfaces: When someone deliberately rotates X-Forwarded-For to dodge limits. | Deployment trust boundary (which proxy hop is trusted) is not yet pinned. | Read the client IP from the verified proxy hop / CDN header; document the topology. | High | Open | Tech Lead / Founder | 10/06/2026 |  |  |  |  | Hardens every IP-based limit (login, booking, AI chat) against header spoofing.
BE-003 | Pre-Development | Reliability / Design | Decide fail-closed vs fail-open for Redis-backed controls | _enforce_hotel_ai_quota and the limiter intentionally fail OPEN if Redis is unreachable so real guests aren't blocked — a deliberate availability choice that trades away cost protection during an outage. ⏱ When it surfaces: Only during a Redis outage coinciding with a traffic/abuse spike. | Availability prioritised over cost-safety; no conservative fallback budget. | Add a conservative in-process fallback cap for cost-bearing controls; alert on Redis health. | Medium | Open | Tech Lead / Founder | 10/06/2026 |  |  |  |  | Keeps a floor of abuse/cost protection even when Redis is briefly unavailable.
BE-004 | Pre-Development | Capacity Planning | Run the peak-load test before go-live | A ready load-test script (scripts/load_test.py) and a sizing guide (SCALE_TUNING.md) exist; the test simply needs to be executed at expected peak and the pool/concurrency tuned to the result. ⏱ When it surfaces: At the first real high-traffic moment (sale, campaign, festival). | Go-live checklist item still open. | Run load_test.py on staging at expected peak; set WEB_CONCURRENCY and pool under the Supabase limit. | High | Open | Tech Lead / Founder | 10/06/2026 |  |  |  |  | Turns the scaling ceiling into a known number instead of discovering it during a live spike.
BE-005 | Pre-Development | Capacity Planning | Validate the DB connection budget for AI/streaming workloads | Default pool is ~10 conns/worker. AI chat keeps a DB session open during the LLM call, so effective AI concurrency is lower than the raw pool math suggests. ⏱ When it surfaces: As concurrent AI chats rise across busy hotels. | Connection math assumes short requests; long AI requests were not separately modelled. | Model AI concurrency separately; size pool vs Supabase limit; combine with the streaming/session work below. | Medium | Open | Tech Lead / Founder | 10/06/2026 |  |  |  |  | Prevents connection-pool pressure from AI traffic affecting the rest of the API.
BE-006 | Pre-Development | Team / Ownership | Assign dedicated backend & frontend engineering ownership | The platform is large (~70 routers, 250+ endpoints, payments, multi-tenant, AI). Today there is no named owner for backend reliability or frontend UX/performance. ⏱ When it surfaces: Continuously — every unowned issue ages without a clear owner. | Project scope outgrew the team. | Hire 1 backend + 1 frontend engineer (scoped on the 'Team & Hiring' sheet). | High | Open | Tech Lead / Founder | 10/06/2026 |  |  |  |  | Faster fixes, lower single-maintainer risk, and the Hypercare SLAs become achievable.
BE-007 | Development | AI Agent / Bug | Hotelier AI Assistant crashed on every message (missing logger) | agent.py referenced a module-level `logger` (smart tool selector + settings fetch) that was never defined, so any non-empty query raised NameError and returned 500. ⏱ When it surfaces: Was firing on 100% of hotelier assistant messages. | Missing logging.getLogger in app/core/agent.py. | Add the module logger; add a regression smoke test on the tool-selector path. | Critical | Resolved | Backend Dev | 10/06/2026 |  | 10/06/2026 | Added module-level logger in app/core/agent.py; added tests/test_ai_agent_smoke.py asserting the tool-selector path never raises NameError. Full suite green (253 passed). |  | FIXED: the paid hotelier AI assistant is restored. This was the single biggest functional bug.
BE-008 | Development | AI / Scaling | AI chat holds a DB connection for the whole LLM round-trip | chat.py/agent.py keep the request DB session open while agent.arun() runs (seconds, 1-2 calls) because the agent's tools query the DB mid-call. ⏱ When it surfaces: When many guests chat at the same time (e.g. a campaign). | Request-scoped session spans the slow LLM I/O instead of using short per-tool sessions. | Refactor tools to short-lived sessions / pre-fetch data and release the session before the model call. | High | Open | Backend Dev | 10/06/2026 |  |  |  |  | Once addressed, AI concurrency stops competing with the rest of the API for DB connections.
BE-009 | Development | AI / Cost | Error fallback escalated to the expensive 70B model | On any guest-agent error, chat.py retried (without tools) and defaulted to llama-3.3-70b-versatile — pricier than the normal 8B path — after already paying for the failed call. ⏱ When it surfaces: During any transient provider/tool error, multiplied under load. | Fallback defaulted to a large model. | Keep the fallback on the cheap 8B model; single attempt. | High | Resolved | Backend Dev | 10/06/2026 |  | 10/06/2026 | chat.py fallback now defaults to llama-3.1-8b-instant (cheap) instead of the 70B model. |  | FIXED: error storms no longer cost ~2x and no longer jump to a costlier model.
BE-010 | Development | AI / Reliability | Web-search tool could block the worker (sync call, no timeout) | agent.py search_web called DuckDuckGo synchronously on the event loop with no timeout. ⏱ When it surfaces: Whenever the hotelier asks a 'why' question that triggers web search and DDG is slow. | Blocking external call with no SLA on the async loop. | Run it in a thread with a hard timeout; degrade gracefully. | High | Resolved | Backend Dev | 10/06/2026 |  | 10/06/2026 | search_web now uses asyncio.to_thread + asyncio.wait_for(8s) and returns a graceful message on timeout/failure. |  | FIXED: a slow search can no longer stall the worker for other users.
BE-011 | Development | AI / Authorization | Make destructive AI actions confirm in code, not just in the prompt | cancel_booking / update_room_price / create_promo_code rely on a prompt instruction to 'ask first'. Nothing in code enforces it, so a model slip or injected text could execute them. ⏱ When it surfaces: If a guest/hotelier message is crafted to trick the model, or the model mis-fires. | Confirmation is a prompt convention, not a code gate. | Require an explicit 2-step confirmation token in code before any mutating tool runs; gate price/promo behind OWNER/MANAGER. | High | Open | Backend Dev | 10/06/2026 |  |  |  |  | Hardening: removes the chance of an AI-initiated cancellation or rate change without a real confirmation. (Tenant scope already enforced.)
BE-012 | Development | AI / Security | Harden the bots against prompt injection | Guest chat text reaches a tool-enabled LLM, and chain guest_history (incl. guest special_requests) is injected into the system prompt — a path for second-order injection. ⏱ When it surfaces: As real guests (and the occasional bad actor) type free-form messages. | Untrusted text concatenated into prompts that can drive tools. | Treat guest/stored text as untrusted; sanitise before insertion; keep public-bot tools read-only; add injection tests. | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Protects against the bot being steered to misquote prices/policies or reveal unintended info.
BE-013 | Development | AI / Bookings | Re-check availability inside AI quick-booking | create_quick_booking writes a Booking without an inventory/overlap check (availability is a separate optional tool the model may skip). ⏱ When it surfaces: When the AI books a date range that's actually sold out. | Booking tool does not re-validate availability atomically. | Re-check availability inside create_quick_booking and reject on conflict. | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Prevents AI-driven overbooking and the resulting walk/compensation cost.
BE-014 | Development | Performance | Optimise availability counting (currently in-Python loops) | check_availability does an O(bookings*rooms) Python loop over overlapping bookings (rooms are stored as a JSON array). ⏱ When it surfaces: On large/busy hotels with many overlapping bookings. | In-memory aggregation; fine for small data, heavier as bookings grow. | Pre-aggregate counts; ensure composite index on (hotel_id, status, dates). | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Keeps the booking funnel and concurrent chats fast as data volume grows.
BE-015 | Development | AI / Accuracy | Validate AI-quoted prices/policies against the DB | The bots generate free text; tools exist but nothing guarantees a quoted price/policy exactly matches the DB. (Checkout already re-validates price server-side.) ⏱ When it surfaces: When a guest asks detailed price/policy questions and the model paraphrases. | Generative output is not constrained to tool data. | Post-check any price/availability the model states before sending it to the guest. | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Reduces the risk of a guest treating a wrong AI quote as a commitment.
BE-016 | Development | AI / UX | Make chart data flow through code, not model echo | agent.py asks the model to echo [CHART_DATA] JSON verbatim; smaller models sometimes reword or drop it. ⏱ When it surfaces: Intermittently, depending on the model and prompt. | Structured output delegated to model obedience. | Return chart data via a dedicated field the UI reads directly. | Low | Open | Backend Dev | 10/06/2026 |  |  |  |  | Dashboard charts render reliably -> hoteliers trust the analytics.
BE-017 | Development | AI / Config | Require explicit AI provider instead of key-prefix guessing | Provider is inferred from key prefixes (gsk_/sk-/AIza); a custom gateway or new key format breaks selection. ⏱ When it surfaces: When a hotel rotates keys or uses a non-standard provider. | Heuristic detection instead of explicit config. | Require ai_provider; use prefix detection only as a logged last resort. | Low | Open | Backend Dev | 10/06/2026 |  |  |  |  | Avoids a hotel's AI silently routing to the wrong API after a key change.
BE-018 | Development | AI / Cost | Confirm model tiering for the hotelier assistant | The hotelier assistant defaults to a 70B model. Policy allows a large model for the analytics agent; confirm whether general assistant traffic should use the cheap model with large reserved for heavy analytics. ⏱ When it surfaces: Linearly with hotelier assistant adoption. | Default model choice vs cost policy needs a product decision. | Default general queries to the cheap model; route only heavy analytics to 70B. | Low | Open | Backend Dev | 10/06/2026 |  |  |  |  | Optional cost optimisation; pairs with the AI-budget item.
BE-019 | Development | Privacy / Logging | Stop logging PII at INFO in the auth path | deps.py logged email/supabase_id at INFO on several auth branches; policy is DEBUG-only / hashed. ⏱ When it surfaces: Continuously in production logs until changed. | Verbose INFO logging of identifiers on the hot auth path. | Drop to DEBUG / log non-PII identifiers; keep LOG_LEVEL=WARNING in prod. | Medium | Resolved | Backend Dev | 10/06/2026 |  | 10/06/2026 | deps.py auth logs with email/supabase_id moved to DEBUG; master-admin promotion now logs user_id instead of email. |  | FIXED: lowers PII exposure and log egress cost.
BE-020 | Development | Reliability / SSE | Add a max lifetime + disconnect check to streaming chat | stream_guest_ai streams agent events with no overall timeout and holds the DB session for the whole stream; only tool_call_limit bounds it. ⏱ When it surfaces: With abandoned/idle streaming chats or deliberate slow clients. | Missing max-duration and client-disconnect handling on the SSE generator. | Add a hard stream lifetime + disconnect detection; release the session before streaming. | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Frees worker+DB resources held by dead streams; raises real concurrency.
BE-021 | Development | Observability | Strengthen AI usage accounting | record_ai_usage swallows all errors and returns 0 if metrics/Redis are missing, so a failed run may record nothing. ⏱ When it surfaces: When Redis or metrics are briefly unavailable. | Telemetry is best-effort with no fallback/alert. | Emit a metric on accounting failures; keep a durable aggregate beyond Redis. | Low | Open | Backend Dev | 10/06/2026 |  |  |  |  | Keeps cost dashboards trustworthy so overspend isn't hidden.
BE-022 | Development | Error Handling | Stop returning raw exception text to clients | The assistant endpoint returned HTTP 500 with detail=f'AI Agent Error: {str(e)}', leaking internal error text. ⏱ When it surfaces: On any unhandled agent error. | Generic except surfaced internal detail in the response. | Return a generic message; log detail server-side. | Medium | Resolved | Backend Dev | 10/06/2026 |  | 10/06/2026 | api/v1/agent.py now returns generic 500/503 messages and logs full detail server-side with exc_info. |  | FIXED: no internal stack/library detail leaks to callers.
BE-023 | Post-Development | Scaling / Outage | Protect against DB connection exhaustion under a traffic burst | SCALE_TUNING.md flags Postgres connections as the #1 crash risk. A burst of page loads (search + availability + chat warm) on one popular hotel can pressure the pool (default ~10/worker). ⏱ When it surfaces: When ~100 users hit one hotel page at once (campaign/QR/sale). | Small connection budget + AI requests holding connections longer. | Right-size pool/concurrency under the Supabase limit; release sessions early; add a CDN/cache for public reads. | High | Open | Backend Dev | 10/06/2026 |  |  |  |  | Prevents one hotel's success from degrading the whole platform.
BE-024 | Post-Development | Abuse / Cost | Add a non-spoofable signal to the public AI chat | chat/guest is anonymous; the 5/min IP limit is spoofable and the real cap is 1000 LLM calls/hotel/day (which fails open without Redis). ⏱ When it surfaces: If a bot targets the public widget, or it's left open and looping. | Spoofable IP limit + fail-open quota on an unauthenticated, cost-bearing endpoint. | Add a signed widget token / captcha, a fail-closed quota, and a platform-wide spend breaker. | High | Open | Backend Dev | 10/06/2026 |  |  |  |  | Caps the worst-case LLM bill from automated abuse of the public chat.
BE-025 | Post-Development | Abuse / DoS | Add a baseline rate limit to authenticated routes | Login is on Supabase (no backend password endpoint), but most authenticated routes have no limiter, and invalid Bearer tokens are uncacheable so each forces a JWT verification. ⏱ When it surfaces: Under a deliberate token-flood. | Rate limiting applied selectively; auth verify cost paid per garbage-token request. | Add an IP+token baseline limit; short-cache negative verifications; alert on auth-error spikes. | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Keeps latency stable for real hoteliers during an auth-spam attempt.
BE-026 | Post-Development | Reliability / SPOF | Make Redis highly available | Payment idempotency, rate limits, AI quota, auth cache and analytics caches all rely on a single Redis instance (SCALE_TUNING notes HA is needed before relying on it for payment idempotency). ⏱ When it surfaces: During any Redis outage. | No Redis HA; several controls degrade on its loss. | Move to managed HA Redis; define explicit degraded-mode behaviour per control. | High | Open | Backend Dev | 10/06/2026 |  |  |  |  | Removes a single point that simultaneously weakens abuse limits, AI quota and payment idempotency.
BE-027 | Post-Development | Cost Monitoring | Automate per-hotel AI spend alerting | The ai_tokens counters exist but must be read manually; no threshold alert or auto-throttle. ⏱ When it surfaces: As AI usage scales and one hotel/bot spikes. | Monitoring is manual. | Add daily aggregation + alerts + optional auto-throttle at the tier budget. | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Overspend is caught in hours, not on the monthly invoice.
BE-028 | Post-Development | Cost / Scale | Raise AI cache hit-rate to flatten cost growth | Each guest message is 1-2 LLM calls; only a short-TTL cache dedupes. Cost grows with visitor volume. ⏱ When it surfaces: As marketing succeeds and visitor numbers climb. | Variable per-message LLM cost with limited dedup. | Increase cache hit-rate, keep prompts/history tight (history already capped at 20), set a platform spend breaker. | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Keeps AI cost growing slower than traffic.
BE-029 | Post-Development | External Dependencies | Add timeouts/retries + alerting to third-party calls | Weather, DuckDuckGo, Razorpay, Google Sheets (fire-and-forget) and Meta can fail; some failures are swallowed (sheet sync), losing data silently. ⏱ When it surfaces: During any provider outage or slowdown. | No circuit breakers/retries; fire-and-forget drops failures. | Add timeouts, retries with backoff, and a dead-letter/alert for failed syncs. | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Prevents silent lead-data loss and provider-outage error spikes for guests.
BE-030 | Post-Development | Data Quality | Validate ingested competitor rates (rate-shopper) | Rate-shopping data comes from the Chrome extension; if it stalls or sends bad data, pricing advice rests on stale/garbage rates. ⏱ When it surfaces: When the scraper breaks or a competitor site changes. | External ingestion with limited validation. | Validate/timestamp ingested rates; flag stale data; bound ingestion volume. | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Keeps AI pricing recommendations based on fresh, sane data.
BE-031 | Post-Development | Payments / Security | Keep payment webhook signature verification locked down | Payment confirmation trusts HMAC-verified webhooks (Razorpay/Meta). This must stay correct as code evolves. ⏱ When it surfaces: Only if a future change weakens verification. | Security-critical path that must not regress. | Add tests asserting signature rejection; alert on verification failures; keep strict per-hotel keys. | High | Open | Backend Dev | 10/06/2026 |  |  |  |  | Protects directly against spoofed 'paid' events / financial loss.
BE-032 | Post-Development | Multi-tenancy | Add automated tests for tenant isolation in AI tools | AI tools filter by user.hotel_id today; a future tool that forgets the filter would leak/modify another hotel's data. ⏱ When it surfaces: Only if a future tool drops the hotel_id filter. | Isolation enforced per-query; easy to miss on new tools. | Add a shared tenant-scoping helper + tests asserting cross-hotel access is blocked for every AI tool. | High | Open | Backend Dev | 10/06/2026 |  |  |  |  | Locks in the core 'one hotel never sees another' guarantee against regressions.
BE-033 | Post-Development | Memory / Cost | Offload report/PDF generation to a background worker | Reports load pandas/matplotlib/reportlab (lazy but heavy) in-request; concurrent exports inflate per-worker RAM. ⏱ When it surfaces: When several hoteliers export analytics at once on a small box. | Heavy, CPU/RAM-intensive work done in the request path. | Move generation to a background worker/queue; cap concurrency. | Medium | Open | Backend Dev | 10/06/2026 |  |  |  |  | Avoids worker OOM/restarts dropping in-flight requests.
BE-034 | Post-Development | Monitoring | Alert when the AI falls back to its canned error message | On failure the bots return friendly text and log the error; without alerting, sustained failures look like normal traffic. ⏱ When it surfaces: During a quiet AI/provider outage. | Graceful degradation without a paired alert. | Emit an error metric whenever the canned fallback fires; alert on rate. | Low | Open | Backend Dev | 10/06/2026 |  |  |  |  | The AI can't be silently down for hours; issues surface before customers complain.

## Load & Cost Scenarios
⚡ Load, Abuse & Cloud-Cost Scenarios — 'what happens if…'
Scenario | Trigger | What happens technically (code-grounded) | Business impact | Current safeguard | Recommended hardening
100 users on one hotel page at once | Campaign/QR/sale drives a burst to one page. | Each visit can fire room search + availability + AI widget warm. Availability counts in Python; AI chat holds a DB connection for the whole LLM call. Default pool ~10/worker. | If the pool saturates, requests queue/timeout -> 500s for ALL hotels until it drains. | Per-worker pool, lazy heavy imports, short caches, documented connection math, 60-120/min public read limits. | Release DB session before the LLM call; CDN/cache public reads; right-size pool/concurrency; run the load test.
Bot spams the public AI chat | Anonymous attacker scripts the widget, rotating X-Forwarded-For. | 5/min IP limit is spoofable; backstop is 1000 LLM calls/hotel/day, which fails open without Redis. Each message = 1-2 LLM calls. | Worst-case a few $/day of LLM per targeted hotel; bounded by the daily cap unless Redis is down. | Per-hotel daily cap (1000), feature flag, cheap 8B model, token accounting, fixed cheap fallback. | Signed widget token/captcha; fail-closed quota; platform-wide spend breaker.
Someone spams the backend auth | Flood of authenticated routes with garbage Bearer tokens. | Login is on Supabase (no backend password endpoint). Invalid tokens are uncacheable so each runs a JWT verify; most authed routes have no rate limit. | CPU + Supabase auth load climb; latency degrades for real hoteliers. | Valid-token payload caching; active-session tracking; Supabase verifies signature+exp; PII now logged at DEBUG. | Baseline IP+token limit on authed routes; short negative-cache; alert on auth-error spikes.
Redis goes down | Single Redis instance restarts/blips. | Rate limits, AI quota, auth cache, slug/analytics caches and payment idempotency degrade; quota+limits fail open. | Abuse/cost protection drops; payment idempotency loss risks double-charges. | Best-effort try/except keeps the app serving. | Managed HA Redis; explicit fail-closed for cost/payment controls; Redis health alerting.
AI adoption grows (marketing works) | More guests use the concierge across more hotels. | Variable cost = 1-2 LLM calls/message; limited dedup (short cache). | LLM bill grows with traffic; margins compress without a budget. | Cheap 8B default on guest bot, history capped at 20, tool/token caps, usage counters. | Per-tier budget + auto-throttle; higher cache hit-rate; bill pass-through decision.
Concurrent report/PDF exports | Several hoteliers export analytics at once. | pandas/matplotlib/reportlab load per worker (lazy but heavy); CPU/RAM intensive in-request. | Small boxes can OOM and restart workers, dropping in-flight requests. | Lazy imports keep idle RAM low. | Background worker/queue for generation; cap concurrent exports.

## CI-CD Pipeline
🔄 CI/CD Pipeline — automated quality gates
GitHub Actions runs on every Pull Request and on pushes to main/develop/feature branches. A change cannot merge unless these gates pass — this is what stops a bug like the AI-assistant crash from ever reaching production again.
Stage | Tool / Action | What it checks | Why it matters here
Trigger | GitHub Actions (push + pull_request) | Runs automatically on PRs and branch pushes (main/develop/claude/**). | Every change is checked before merge, not after deploy.
Backend - Install | pip install -r requirements.txt (Python 3.11) | Dependencies resolve and install cleanly. | Catches broken/missing dependencies early.
Backend - Compile | python -m compileall app main.py | Fast-fails on any syntax or import error across the backend. | Would have instantly caught the missing-logger class of bug.
Backend - Tests | pytest tests/ (253 passing) | Runs the full backend suite incl. the new AI smoke/regression tests. | Pins the AI-assistant fix and guards multi-tenant/payment behaviour.
Frontend - Types | tsc --noEmit | TypeScript type-checks the whole frontend. | Catches UI/data-shape errors before build.
Frontend - Build | npm run build (Vite) | Production build succeeds. | Ensures the app actually ships.
Frontend - E2E | Playwright (chromium) | End-to-end browser tests of key flows. | Verifies real user journeys (incl. booking/AI UI).
Artifacts | upload-artifact | Stores the Playwright report for 30 days. | Failures are debuggable from the PR.
Deploy (CD) | Railway (create_all on boot) | Deploys backend+frontend; DB tables via create_all. | Roadmap: add a staging gate + smoke check before prod promotion.
Recommended next CI/CD additions
1. Add pip-audit / npm audit (dependency vulnerability scan) as a non-blocking gate, then enforce.
2. Add a staging environment + automated smoke test before promoting to production (true CD).
3. Add coverage reporting and a minimum threshold so AI/payment paths stay tested.
4. Add a secrets-scanning step (e.g. gitleaks) to prevent keys being committed.

## Team & Hiring
👥 Team & Hiring Recommendation
Recommendation: YES — hire one Backend Engineer (priority) and one Frontend Engineer. The platform is large (~70 routers, 250+ endpoints, payments, multi-tenant, AI). The critical AI-assistant bug is already fixed; the remaining roadmap is mostly backend reliability/cost/security plus frontend UX/perf. Dedicated owners make the Hypercare SLAs achievable.
Role | Why needed (tied to issues) | What they own in THIS project | First 30 / 60 / 90 days
Backend Engineer (Python/FastAPI) — PRIORITY | Owns the High/Medium backend roadmap: DB session held during LLM (BE-008), code-level confirmation on mutating tools (BE-011), prompt-injection hardening (BE-012), AI abuse/rate limits (BE-024/025), Redis HA (BE-026), tenant-isolation tests (BE-032), webhook integrity (BE-031). | FastAPI services, AI agents (agno), Postgres performance & indexing, Redis, payments/Razorpay, multi-tenant security, rate limiting, cost controls, tests, observability. | 30d: rate-limit authed routes, ship fail-closed AI quota. 60d: release DB session before LLM, prompt-injection + code confirmations, SQL-aggregate availability. 90d: cost alerts/auto-throttle, Redis HA, load test + scaling tune.
Frontend Engineer (React/Vite) | Owns the guest booking experience and hotelier dashboard quality: chart pipeline (BE-016), AI chat/streaming UX, graceful error/loading states, and the conversion-critical booking funnel. | React/Vite app, booking engine UI, AI chat widget + SSE streaming UI, analytics charts, error/empty/loading states, accessibility, performance (bundle/CDN), frontend telemetry. | 30d: robust error/loading states for AI + booking; fix chart rendering. 60d: streaming UX + disconnect handling; booking funnel polish. 90d: performance + accessibility pass; funnel drop-off analytics.
(Optional) Fractional DevOps / SRE | Infra-flavoured items: Redis HA (BE-026), pool exhaustion (BE-023), trusted proxy/WAF (BE-002/024), load test (BE-004), report worker (BE-033). | Railway/infra, Supabase connection budget, Redis HA, CDN/WAF, monitoring/alerting (Sentry), CI/CD, load testing. | Can be contract or absorbed by the senior backend hire initially; formalise before scaling traffic.

## Phase Plan
🏨 Booking Engine — Phase-wise Delivery Plan
Phase | Milestone / Activity | Owner | Start Date | End Date | Duration (days) | Status | Notes
Pre-Development | Architecture & cost-governance review (AI budget, trust model) | Tech Lead |  |  |  | Not Started
Pre-Development | Capacity plan + DB connection budget vs Supabase limit | Backend Dev |  |  |  | Not Started
Pre-Development | Run load test at expected peak (scripts/load_test.py) | DevOps |  |  |  | Not Started
Pre-Development | Hiring: backend + frontend engineers | Founder |  |  |  | Not Started | See Team sheet
Pre-Development | Define abuse/rate-limit & fail-closed policy | Backend Dev |  |  |  | Not Started
Development | Fix AI assistant crash (logger) + smoke tests | Backend Dev | 10/06/2026 | 10/06/2026 | 0 | Completed | DONE - 253 tests green
Development | Cheap-model error fallback + web-search timeout | Backend Dev | 10/06/2026 | 10/06/2026 | 0 | Completed | DONE
Development | Sanitise error responses + PII logging to DEBUG | Backend Dev | 10/06/2026 | 10/06/2026 | 0 | Completed | DONE
Development | Release DB session before LLM round-trip | Backend Dev |  |  |  | Not Started
Development | Prompt-injection hardening + code-level confirmations | Backend Dev |  |  |  | Not Started
Development | Performance: SQL aggregation + indexes | Backend Dev |  |  |  | Not Started
Development | Frontend: chart pipeline, error/loading UX | Frontend Dev |  |  |  | Not Started
Development | QA + automated coverage for AI/payment paths | Both Devs |  |  |  | Not Started
Post-Development | Redis HA + fail-closed quota | DevOps |  |  |  | Not Started
Post-Development | Cost monitoring + per-hotel spend alerts | Backend Dev |  |  |  | Not Started
Post-Development | WAF / signed widget token / captcha for public AI | Backend Dev |  |  |  | Not Started
Post-Development | Scaling tune (pool/concurrency/replicas) + CDN | DevOps |  |  |  | Not Started
Post-Development | Hypercare monitoring & SLA tracking (30 days) | Both Devs |  |  |  | Not Started
Post-Development | Background worker for reports/PDF + dead-letter syncs | Backend Dev |  |  |  | Not Started
Post-Development | CI/CD: staging gate + dependency/secret scanning | DevOps |  |  |  | Not Started | CI already on PRs

## Priority Matrix
Issue Priority Matrix — Definitions & Resolution SLAs
Priority | Definition | Examples | Response SLA | Resolution SLA | Owner | Escalation
Critical | Breaks core money/data flow or takes the platform down; no workaround. | AI assistant 500s on every call (now fixed); DB pool exhaustion; spoofed payment webhook; cross-tenant leak. | Immediate (< 1 h) | 4 h (same day) | Tech Lead | Founder
High | Major feature broken or a real cost/abuse/security risk. | DB connection held during LLM; public AI abuse; Redis SPOF; no rate limit on authed routes. | 2 h | 24 h | Tech Lead | Founder
Medium | Degraded behaviour, performance or hygiene; limited blast radius. | Availability loops; SSE lifetime; PII at INFO (now fixed); provider detection. | 4 h | 3 business days | Tech Lead | Tech Lead
Low | Cosmetic/observability/low-likelihood; fix when convenient. | Chart echo; usage accounting; canned-error alerting. | Next sprint | 1–2 sprints | Tech Lead | Tech Lead
COLOUR LEGEND
Critical | High | Medium | Low | Pre-Dev Phase | Dev Phase | Post-Dev Phase

## Dashboard
Booking Engine — Issue Summary Dashboard
Update the Issue Tracker sheet; this dashboard auto-calculates totals
ISSUES BY STATUS |  | ISSUES BY PRIORITY
Status | Count | Priority | Count
Open |  | Critical
In Progress |  | High
Blocked |  | Medium
Resolved |  | Low
Closed
Deferred
TOTAL
ISSUES BY PHASE
Phase | Count
Pre-Development
Development
Post-Development

## Timeframes
Recommended Timeframes for Issue Resolution
Phase | Issue Type | Priority | Discovery Method | Target Fix Window | Notes
Pre-Development | Architecture/cost-governance gap | Critical | Design review | Before dev | Blocks safe build
Pre-Development | Capacity/connection planning | High | Load test | Before go-live | Sets scaling ceiling
Pre-Development | Trusted-proxy / IP trust | High | Security review | Before go-live | Affects every IP limit
Pre-Development | Team/ownership gap | Medium | Mgmt review | This quarter | Staffing decision
Development | AI agent crash / 500 | Critical | Smoke test / QA | < 1 day (DONE) | Was feature-down; fixed
Development | Connection held during LLM | High | Load test / profiling | 1 sprint | Scaling root cause
Development | Prompt injection / tool authz | High | Security test | < 1 sprint | Money/data at risk
Development | Performance (loops/N+1) | Medium | Profiling | 1-2 sprints | Latency under load
Development | Cost (model/fallback) | High | Cost review | DONE | Fixed: cheap fallback
Development | Privacy/logging hygiene | Medium | Code review | DONE | Fixed: PII to DEBUG
Post-Development | Pool exhaustion / outage | Critical | Monitoring/alert | Immediate (<1h) | Hypercare SLA
Post-Development | Payment webhook integrity | Critical | Security test | Immediate | Financial loss
Post-Development | Abuse / DoS / cost spike | High | Monitoring/WAF | < 24h | Cost + availability
Post-Development | Cost monitoring/alerting | Medium | Dashboards | 1-2 sprints | Late detection
Post-Development | Redis HA / SPOF | High | Infra review | < 1 sprint | Multi-control failure
Post-Development | External dependency failure | Medium | Retries/alerts | 1-2 sprints | Data loss/UX
Post-Development | Tenant isolation regression | Critical | Security test | Immediate | Data breach
Post-Development | Observability gaps | Low | Metrics | Next sprint | Slow detection

## How to Use
How to Use This Tracker
Issue Tracker | Main working sheet. Add every bug/error here. • Use dropdown menus for Phase, Priority and Status columns. • ID is auto-assigned (BE-001, BE-002 …); enter dates in DD/MM/YYYY. • Time to Fix calculates automatically once Reported & Resolved dates are filled. • Keep 'Resolution Notes' updated — the team will use it as a knowledge base.
Phase Plan | High-level delivery roadmap. • Add Start and End dates for each milestone — Duration auto-calculates. • Use the Status dropdown (Not Started / In Progress / Completed / Blocked / Deferred). • Update regularly during sprint reviews.
Priority Matrix | Reference sheet — do not edit. • Defines what Critical / High / Medium / Low mean for this project. • Response and Resolution SLAs are binding during Hypercare (30 days post-launch). • Use the colour legend at the bottom when reviewing any sheet.
Dashboard | Auto-calculated summary — do not edit directly. • Counts update as you fill in the Issue Tracker. • Share a screenshot of this tab in weekly status reports. • If counts look wrong, ensure Phase / Priority / Status values match the dropdowns exactly.
Timeframes | SLA reference for every combination of phase and priority. • Use this when setting Target Dates in the Issue Tracker. • Deviation from these windows must be approved by the Tech Lead and logged in Remarks.
How to Use | This sheet. Pin to your browser tab and share with all team members before the first sprint.