## Summary
Staybooker — Work Completed & Business Impact
Actual code changes delivered (PR #54) + earlier fixes (PR #53, merged). Every item is implemented, verified (frontend build + 265 backend tests green), and ready to ship. Prepared for CEO / Leadership · 2026-06-10.
What | Count | Detail
Public booking-page bugs fixed (this PR) | 5 | Fake 'Sold Out', fake calendar prices, data-leak, blank-page-on-error, date validation
Backend scale/cost optimizations (this PR) | 2 | Availability index + fail-closed AI cost cap
Backend defects fixed earlier (merged) | 5 | AI assistant crash, web-search block, costly fallback, error leak, PII logging
Automated tests | 265 passing | +12 new (secret-masking, AI cost, quota fallback)
CI/CD | Strengthened | coverage + CVE scan + compile gate, runs on PRs
Frontend build | Green | tsc + vite build pass
Total code files changed (this PR) | 7 | 5 frontend + 2 backend

## Code Changes (Done)
1. Code Changes Delivered — PR #54
Each row is an actual, verified code change in this PR. 'Impact' is the business effect. All items: Status = Done.
ID | Area | Problem (before) | File(s) | What we changed | Business impact | Severity | Status
CH-01 | Public Widget | Fake 'Sold Out' every 13th of the month | frontend/.../ModernFloatingLayout.tsx, ChainBookingWidget.tsx | Removed hardcoded date===13 sold-out logic; widget no longer shows false unavailability | Available rooms were shown 'Sold Out' on the 13th every month → direct booking loss now stopped | Critical | Done
CH-02 | Public Widget | Fake calendar prices (placeholder 4200 + invented weekend +500) | ModernFloatingLayout.tsx, ChainBookingWidget.tsx | Show only the real starting ('from') rate; removed the fabricated weekend surcharge and 4200 fallback | Guests now see truthful prices → no price shock / mismatch at checkout, higher trust & conversion | Critical | Done
CH-03 | AI Chat Widget | Booking/checkout data broadcast to wildcard origin ('*') | ChatWidget.tsx, ChainBookingWidget.tsx | postMessage now targets the embedding parent's origin (referrer-derived) instead of '*' | Guest booking data no longer exposed to an arbitrary embedding site → privacy/security improved | High | Done
CH-04 | Room Selection | Room fetch failure showed a silent blank page; add-on outage blanked the whole page | BookingSelection.tsx | Added an explicit error + Retry screen; made add-ons load non-blocking | Guests hitting a transient error can recover instead of abandoning; an add-on outage no longer kills the page | High | Done
CH-05 | Booking Widget | Search allowed with missing/inverted dates -> empty results page | useBookingWidgetState.tsx, ChainBookingWidget.tsx | Validate a real date range before navigating; otherwise re-open the calendar | Fewer dead-end empty searches; cleaner funnel | Medium | Done
CH-06 | Backend / Scale | Availability query (hottest path) lacked a status-aware composite index | backend/app/core/database.py | Added index on bookings (hotel_id, status, check_in, check_out) | Keeps availability fast as bookings grow to large volumes — key for 1000+ concurrent users | Medium | Done
CH-07 | Backend / Cost | AI per-hotel daily cost cap failed OPEN when Redis was down | backend/app/api/v1/public/chat.py | Added a conservative in-process fallback cap (fail-closed-ish) when Redis is unavailable | An abuse spike during a Redis outage can no longer burn unbounded LLM spend | High | Done

## Earlier Fixes (Merged)
2. Earlier Fixes — already merged (PR #53)
Context: these shipped before this PR and are live in main.
ID | Problem | File | What we changed | Business impact | Severity | Status
EF-01 | AI assistant 500'd on EVERY message (undefined logger) | app/core/agent.py | Defined the module logger + regression test | Restored a paid feature that was 100% down | Critical | Done (merged)
EF-02 | Web-search blocked the worker (sync, no timeout) | app/core/agent.py | Thread + 8s timeout, graceful degrade | One slow API can't freeze a worker | High | Done (merged)
EF-03 | Error fallback used the ~10x pricier 70B model | app/api/v1/public/chat.py | Keep fallback on the cheap 8B model | Error storms no longer multiply AI cost | High | Done (merged)
EF-04 | Raw exception text leaked to clients | app/api/v1/agent.py | Generic client message; detail logged server-side | No internal detail leaks to users | Medium | Done (merged)
EF-05 | PII (email/supabase_id) logged at INFO | app/api/deps.py | Moved to DEBUG; log user_id not email | Less PII in production logs | Medium | Done (merged)

## Tests & CI
3. Tests & CI/CD Added
Automated quality checks added/strengthened in this PR.
Item | Type | What it does | Why it matters | Status
test_sensitive_fields.py | Security | Asserts hotelier payloads never expose WhatsApp/SMTP/Razorpay/AI secrets | Guards multi-tenant secret leak | Done
test_ai_usage.py | Cost | Pins the AI token-accounting math | Protects cost visibility from under-counting | Done
test_ai_quota_fallback.py | Cost/Abuse | Verifies the new fail-closed in-process AI cap (CH-07) | Confirms cost protection during a Redis outage | Done
backend-ci.yml | CI/CD | Added coverage (pytest-cov) + pip-audit CVE scan + compile gate; runs on PRs | Regressions & vulnerable deps caught pre-merge | Done
Backend suite | Testing | 265 passing, 1 skipped (+12 vs baseline) | Broader safety net | Done
Frontend | Build | tsc --noEmit clean + vite production build green | UI changes verified to compile & build | Done

## Remaining (Roadmap)
4. Remaining for full 1000+ readiness (honest)
What is NOT yet done. These are infra/architecture items scheduled next — kept transparent so status is accurate.
Item | Priority | Type | Why it matters
Release DB session before LLM round-trip | High | Backend refactor | Decouples AI concurrency from the DB pool
Redis High Availability | High | Infra | Removes the biggest single point of failure
Trusted-proxy IP + rate-limit authed routes | High | Backend | Hardens abuse/DoS resistance
CDN in front of public reads | Medium | Infra | Absorbs traffic spikes beyond Redis cache
Background queue for reports/PDF | Medium | Backend | Protects worker memory at scale
Taxes calculator div-by-zero; dashboard polish | Medium | Frontend | Dashboard correctness (separate from public funnel)
Load test at peak + DB pool sizing | High | DevOps | Establishes the safe concurrency ceiling